## Front cover
Project planner
Local government elections in England
Date:
Author:
Document version:
Reviews:
Name | Role | Date | Sign-off (ü)

## How to use
Using this template
This template project planner is designed to support Returning Officers (ROs) in England in planning for and delivering a local government election, including local ROs administering a combined authority mayoral election in their local area. Your project plan should capture all of the work that you will need to undertake in planning for and delivering an election or any combined polls that may be taking place in your area. This template project plannner is generic and will need to be adapted to reflect your local circumstances and should be read alongside the relevant Commission guidance for Returning Officers, which is available on our website: www.electoralcommission.org.uk/i-am-a/electoral-administrator
Objectives and success measures
Before compiling a detailed list of deliverables and tasks, the objectives of the project need to be established, i.e., what you want to achieve. The plan should be treated as a 'living document' and you should assess whether the stated objectives are being met, updating your plans and processes as necessary. If you are also the ERO, this plan should feed in to your registration plan and public engagement strategy. The template provides some example objectives, which you can adapt and add to to fit your local circumstances.
Deliverables and tasks
Once the objectives have been identified, individual tasks can be planned for and owners allocated to these. This tab identifies a number of example deliverables and tasks that should be undertaken. In addition to the deliverables and tasks identified, you should also add in all other deliverables and tasks you identify as necessary (to do this, highlight a row, right click and select Insert). Tasks that are required to be undertaken at or by a particular time by the statutory timetable are highlighted.
Dependencies and contact details
The delivery of an election is dependent on a number of internal and external service providers. This tab should be populated with the names and contact details of all internal and external service providers.
Evaluation
This tab can be used to inform the evaluation of the election(s) or, if you have not yet reviewed your last electoral event, to inform that review. The example content should be adapted to ensure that it reflects the main deliverables and tasks contained in your plan, and assesses whether your stated objectives have been met. The outcome of this evaluation can then be used to feed back into your project plan for future electoral events.

## Objectives and success measures
Objectives | Tools for measuring success | Achieved (ü) | Comments / supporting evidence
Run the election(s) in accordance with the legislation and Commission guidance (and if you are delivering a combined authority mayoral election, also in accordance with any guidance or directions issued by the CARO) | · Completion of tasks by deadlines
· Plan and risk register reflect key areas set out in guidance (and if you are delivering a combined authority mayoral election, any guidance or directions issued by the CARO)
A good experience for all voters, with anybody who is entitled to vote able to do so | · Feedback from voters
· Feedback from candidates and agents
· Feedback from staff
· Feedback from organisations with an interest in the voting process, including disability organisations
· Plans for delivering public awareness activity
A good experience for all candidates standing for election, with anybody who is entitled to stand able to do so | · Feedback from candidates, agents and political parties
· Plans for briefing and providing information to candidates and agents
Transparency | · Feedback from stakeholders
· Any records that could be of interest to stakeholders and can be made available, are made available
· Clear audit trail
· Communications strategy
Professional delivery | · Project plan
· Risk register
· Management structure
· Record of project team meetings
· Contracts in place for any outsourced work
· Contingency arrangements
Consistency | · Plans
· Training schedule and materials
· Clear management structures and escalation procedures
Accurate results | · Clear audit trail
· Postal vote paperwork
· Ballot paper accounts
· Verification statements
· Worksheets
· Results
Results in which all stakeholders are confident | · Record of complaints
· Feedback from voters, candidates and agents and other organisations with an interest in the election, including disability organisations
· Feedback from staff
· Minutes of evaluation/review and other relevant meetings and lessons learnt document
· No negative media reporting
· No legal challenges

## Deliverables and tasks
Deliverables | Sub-deliverables | Task / Action | Lead officer | Start date | End date | Comments
Learn lessons from previous electoral events | Consider processes used at previous electoral events, and feed lessons learnt into project planning | Consider outcomes from previous electoral events and lessons learnt document
Consider experiences of other areas at previous electoral events, including those managed on a regional basis if appropriate
Plan for any amendments identified as necessary as a result of these reviews
Prepare plans to support the effective delivery of the polls | Identify project aims and objectives, and plan for the tasks that will need to be undertaken to achieve these | Develop, maintain and keep a project plan under review, revise and update as neccessary
Ensure your plan takes account of your objectives and success measures for the election(s)
| Identify and manage risks | Develop, maintain and keep a risk register under review, revise and update as neccessary
| Consider specific context of the poll(s) and identify implications for planning and delivery of the poll(s) | Consider changes in legislation and electoral landscape since the previous polls and the impact of these changes on your plans and processes
Consider how scrutiny from voters, candidates, political parties, and the media, and the possibility of particularly close contests in constituencies/wards, will impact your planning including your integrity, count, and communication planning
Consider projected turnout levels - and keep these under review throughout the election period. At a minimum, assume that the turnout will be not less than the turnout at the last equivalent polls and consider implications of possible higher turnout. In particular, take into account the potential for late engagement and interest in the election by which point the scope for adjusting any plans will be limited.
Where appropriate identify the extent and implications of other elections being held on the same day
Plan for dealing with new or less experienced candidates, agents and political parties
Consider how you will plan to meet expectations around timing of the verification and counting of the votes
Allocate sufficient resources | Financial | Identify projected costs
Reconcile projected costs for activities against the available budget
Are there any additional requirements that need to factored into the budget? Changes to equipment needed or staff? Is funding available?
| Staffing | Consider your staff roles and responsibilities. Identify where you may to need to alter the number of staff you use for certain roles.
As you identify your staffing requirements, also check the recruitment processes you are intending to follow are robust and comply with all legal requirements (for example, by seeking advice from your council's HR department)
Make enquiries about the availability of staff, including whether they would be available on short notice
If you are also the ERO, take into account potential peaks of activity, for example, registration enquiries/applications around any particular campaign activity and registration, absent voting, Voter Authority Certificate and Anonymous Elector's Document deadlines
| Project team | Establish project team and appoint deputies
Identify staff for all roles
Develop contingency plans for unplanned staff absence
| Staffing requirements for specific processes | Determine staffing requirements for specific processes, including polling station, postal voting and verification and count staff
Write to any staff you have used previously and are considering re-appointing, checking availability
Appoint staff and dispatch letters of appointment
| Support staff | Identify support staff and when you anticipate you will need them to begin work on supporting the poll.
Draw up an escalation procedure for complex enquiries with comprehensive FAQs
Appoint support staff and dispatch letters of appointment as appropriate
Provide training to all relevant staff | Training | Ensure project team is familiar with election framework and legislation, and assess training needs particularly around any changes to either legislation, equipment or software systems.
Review FAQs document for project team / support staff / call centre staff. Ensure any changes to legislation, equipment or software operating instructions are updated.
Identify training needs for all other staff
Prepare training schedule
Review and prepare training materials and ensure they reflect any changes to legislation, process or equipment and data protection requirements.
Training of polling station staff
Training of postal vote issuing staff
Training of postal vote opening staff
Training of verification and count staff. At a combined authority mayoral election where the count is not centralised, this should include training on the CARO's count communication protocol and system for transmitting the local totals.
Managing contractors / suppliers | Poll cards / ballot papers / postal ballot packs | Assessment of whether you need to outsource through a cost-benefit analysis
Create a clear specification setting out exactly what is required and by when (see the Commission's contract management checklist) ensuring that any changes to requirements that might affect production are brought to the attenton of suppliers at an early stage.
Commence procurement process or choose a contractor from the council's list of approved contractors
Develop written contract(s) with legal and/or other expert advice
Ensure that data protection is integral in any tender exercise and satisfy yourself that any existing contractors and suppliers are aware of their obligations under data protection legislation
Ensure arrangements are in place and timescales established for: sending data, checking proofs (including live proofs), and attending the issue of postal votes
Make contingency arrangements
Document all stages of the production process, including any variations
Make initial contact with Royal Mail
Identify and book venues | Polling station venues | Conduct an evaluation of the suitability of polling stations. Need to refer to Accessibility guidance to ensure compliance with RO duty.
Identify and book polling stations
Identify and procure any equipment needed to support voters to vote independently. Liaise with experts within the council and any local groups. Be prepared to respond to requests from electors.
Make contingency arrangements, including preparing a list of alternative venues and an emergency protocol
| Postal vote issue and openings | Identify and book venues
Make contingency arrangements, including preparing a list of alternative venues and an emergency protocol
Finalise layout of the premises, taking into account workflows and IT and security requirements
| Verification and count | Confirm arrangements for the organisation and management of the verification and count processes, and plan when and where they are to take place
Identify and book venue as required
Make contingency arrangements, including considering alternative venues and preparing emergency protocols as required
Finalise layout of the premises
Appropriate allocation of electors to polling stations | Managing polling stations | Allocate electors to polling stations (having regard to the Electoral Commission's guidance)
Identification of potential integrity issues | Maintain a good working relationship with local police Single Point Of Contact (SPOC) | Make contact with local police SPOC and consider signing a memorandum of understanding with the police on the joint planning for elections and the reporting and investigating of electoral fraud.
Schedule regular communications and have in place plans to respond to issues that arise, being prepared for the integrity of the elections to be scrutinised.
Review previous security arrangements and identify any risks, and any new or emerging issues that may impact on the delivery of the poll
Make specific arrangements for police presence at polling stations, the verification and the count
| Security of ballot boxes and ballot papers | Arrange for secure storage, including where there is a break in proceedings
Put in place a system to ensure that ballot papers cannot be interfered with during production and once they are 'live'
Encourage participation | Raise awareness | Ensure that you are aware of any national awareness campaigns that are relevant for your poll. Sign up for Roll Call for latest information on timings and resources available to support in the local area.
Plan and coordinate local public awareness activity
Make contact with the communications department at your local council and seek their input and advice about the most appropriate methods of communication to reach your target audience - social media, posters, written information, flyers, raising at community meetings and with partners
Ensure that all outgoing communications provide appropriate contact details to allow anyone to respond and obtain further information
If you are also the ERO, seek out opportunities for working with local partners to encourage registration in under-registered groups and ensuring voters have acceptable photographic ID or know how to apply for the Voter Authority Certificate.
Update and maintain web pages and plan messaging for use on social media (as appropriate) to include information on the election
| Managing enquiries from the public / candidates | Identify and train front line staff to deal with enquiries, provide them with key information (FAQs, locations of polling stations, types of acceptable photographic ID, key dates in the election timetables) and ensure processes are in place to escalate enquiries to the elections team
| Media liaison | Send out press releases to local media to raise awareness
Ensure all necessary equipment and stationery is in place | Stationery / equipment | Prepare checklist of all stationery/equipment to be used
Check general stock levels and conduct equipment audit, procure any new or replacement items.
Liaise with the local authority regarding provision of ballot boxes, fittings and compartments
Prepare ballot boxes and other polling station equipment and forms for collection/delivery
Produce paperwork to be used during the verification and count processes
Test equipment, including equipment to be used for postal vote identifier verification
Ensure all official documents are in place | Poll cards | Arrange for proof-checking of poll cards and covering envelope
If outsourcing poll card production, ensure software can produce data that printers can use
Dispatch data to printers (ensuring system is in place to send updates after interim election notices of alteration and registration / absent voting deadlines)
Have in place a process for proof-checking poll cards
Sign-off proofs
Make arrangements to check actual stationery produced to highlight if any of the signed-off proofs have been inadvertently altered
First dispatch of poll cards
| Postal ballot packs | Arrange for proof-checking of postal vote stationery
Send data to printers (ensuring system is in place to send updates after the second interim notice and the final election notice of alteration to support the prompt dispatch of postal packs to voters)
Sign-off proofs
Commence printing (having ensured systems are in place to communicate data updates resulting from applications received close to the deadline)
Make arrangements to check actual stationery produced to highlight if any of the signed-off proofs have been inadvertently altered
Attend the issue of postal votes to conduct final checks
Print sufficient postal ballot packs to be able to issue replacements as required
Put in place a mechanism to enable you to issue postal packs to any postal voter who notifies you that they will be away by the time their postal vote is due to be delivered and who will be unable to appoint a proxy.
Ensure sufficient postage is included on all postal votes, including those sent overseas
| Ballot papers - will not apply to local ROs administering a combined authority mayoral election where the CARO has decided to print the ballot papers centrally. | Ballot papers prepared in accordance with legislation
Arrange for proof-checking of ballot papers
Dispatch data to printers
Sign-off proofs
Give print-run estimate
Confirm final print-run
Print ballot papers
Make arrangements to check actual stationery produced to highlight if any of the signed-off proofs have been inadvertently altered
| Notices | Prepare notices
Agree a process for providing candidates and agents with a copy of the notices
Make arrangements to print / display notices as required
| Registers and absent voters' lists | Print registers for all polling stations, plus postal and proxy lists
Develop a process for communicating alterations to the register and any emergency proxy applications that are granted on polling day
Prepare and print the Corresponding Number List, the Ballot Paper Refusal List and Voter ID Evaluation Form for each polling station.
Run nomination process and disseminate relevant information to candidates and agents | Nominations | Agree plans for briefing candidates and agents. At a combined authority mayoral election, discuss briefing arrangements with the CARO.
Prepare nomination packs (at a combined authority mayoral election, this will be done by the CARO)
Arrange informal checks of nomination papers (at a combined authority mayoral election, this will be done by the CARO)
Prepare and deliver briefing sessions for candidates. Ensure any relevant information on legislative change since those candidates would have stood for election is included. At a combined authority mayoral election, this could include information on local arrangements - liaise with the CARO.
Prepare written guidance on the election process and your local arrangements for candidates and/or agents as appropriate
Prepare information on calculating the spending limit (including the electorate number), spending returns and declarations
Manage potential enquiries from observers | Access to information | Prepare information for observers on the location and timing of the issue and receipt of postal ballot papers, postal vote opening sessions, the poll and the counting of the votes
Publish notice of election |  | Print, display and upload to website (at a combined authority mayoral election, print, display and upload to website the notice of election as supplied by the CARO) |  | Not later than 25 working days before poll
Nominations open |  | Informal checking of nomination papers (does not apply at combined authority elections unless you are also the CARO) |  | From date stated on the notice of election (at a combined authority mayoral election, this would be from 10am on the day after publication of the notice of election)
Deadline for the delivery of nomination papers |  | Make final determination on validity of nomination papers (does not apply at combined authority elections unless you are also the CARO) |  | 19 working days before poll (4pm)
Deadline for withdrawals of nomination |  | Finalise ballot papers (unless you are the local RO at a combined authority election where the CARO has decided to print ballot papers centrally) |  | 19 working days before poll (4pm)
Prepare statement of persons nominated indicating any candidates who have withdrawn (does not apply at combined authority elections unless you are also the CARO)
Deadline for notification of appointment of election agents |  | Print, display and upload to website notice of appointment of election agents (does not apply at combined authority elections unless you are also the CARO) |  | 19 working days before poll (4pm)
Publication of first interim election notice of alteration |  | If you are not also the ERO, obtain copy of the notice from the ERO |  | 19 working days before poll
Send updates to printers
Issue poll cards and postal votes to those included in this notice of alteration as appropriate
Manage the absent voting process | Postal vote issuing process | Commence first issue of postal ballot packs, ensuring that any overseas postal ballots are prioritised for early issue
Carry out further issues as circumstances demand
| Opening sessions | Confirm number and timing of opening sessions
Inform candidates and postal voting agents of opening sessions, giving at least 48 hours' notice
First opening of postal votes and subsequent opening sessions
Final opening of postal votes, and completion of matching
Publication of statement of persons nominated |  | Print, display and upload to website (at a combined authority mayoral election, print, display and upload to website the notice of election as supplied by the CARO) |  | Not later than 18 working days before poll (4pm)
Publication of second interim election notice of alteration |  | If you are not also the ERO, obtain copy of the notice from the ERO |  | Between 18 working days and 6 working days before poll
Send updates to printers
Issue poll cards and postal votes to those included in this alteration as appropriate
Publication of monthly notice of alteration |  | If you are not also the ERO, obtain copy of the register from the ERO |  | INSERT RELEVANT DATE
Send updates to printers
Issue poll cards and postal votes to those included in this alteration as appropriate
Registration deadline for the polls |  | If you are not also the ERO, obtain data of registrations under the 12 day rule from the ERO |  | 12 working days before poll
Send updates to printers
Deadline for applications for new postal vote and postal proxies and for amendments to existing postal and proxy voting arrangements |  | Send updates to printers |  | 11 working days before poll (5pm)
Publication of notice of poll and situation of polling stations |  | Print, display and upload to website |  | Not later than 6 working days before poll
Deadline for new applications to vote by proxy (not postal proxy or emergency proxies) |  | Send out proxy poll cards as appropriate |  | 6 working days before poll (5pm)
Deadline for Voter Authority Certificate and Anonymous Elector's Document applications |  | Process and issue - depending on determination date decide if any temporary Voter Authority Certificates or Anonymous Elector's Documents need to be issued. |  | 6 working days before poll (5pm)
Publication of final election notice of alteration |  | If you are not also the ERO, obtain copy of the notice from the ERO |  | 5 working days before poll
Issue poll cards and postal votes to those included in this alteration as appropriate
Print final alterations to add to polling station registers.
Determine any Voter Authority Certificate applications from electors added to the register as part of the final notice of alteration.
Deadline for notification of appointment of polling and counting agents |  | Provide secrecy requirements and issue passes |  | 5 working days before poll
First date that electors can apply for replacements for lost postal votes |  | Issue replacements as required |  | 4 working days before poll
Polling day | [5 empty] | Polling hours between 7am and 10pm
Deadline for emergency proxy applications |  | Designate member(s) of staff to liaise with the ERO to communicate decisions on emergency proxies |  | Polling day (5pm)
Deadline for replacement of spoilt or lost postal votes |  | Ensure no more replacement postal votes are issued after this time |  | Polling day (5pm)
Replacements only issued in response to those returned by hand after 5pm the day before polling day
Deadline for alterations to the register due to clerical error |  | Designate member(s) of staff to liaise with the ERO to communicate decisions |  | Polling day (9pm)
Manage the verification and count arrangements | Verification and count | Confirm date, location and timing of the verification and count
Plan to deal with the media focus on the verification and count
Ensure all staff are briefed and trained on the use of any protocols or instructions in relation to the verification and count
Undertake tests and rehearsals of new or different verification or count processes, as necessary
Ensure all equipment (including PA system) is tested and checked in advance of the count
Prepare information for attendees on the processes to be followed
At a combined authority mayoral election where the count is not centralised, ensure that there is an agreed protocol in place for the transmission and receipt of local totals
After the declaration of result | After the declaration of result | Display / publish results
Print, display and upload to website
Arrange for collection of any equipment that may need to be removed
Seal and send to the ERO the election materials as required by law
Securely destroy documents at the appropriate time in accordance electoral law and with your document retention policy
Pay fees to all staff involved
Review meeting with stakeholders to obtain feedback
Carry out thorough evaluation of all processes outlined in the project plan and produce a lessons learnt document
Complete and submit data returns
Account for the election, including payment of creditors
Return Electoral Commission feedback forms

## Dependencies & contact details
| Department/ Service/ Company/ | Contact name | Phone number | E-mail address
ERO (if you are not also ERO) | E.g. ERO, deputy EROs
Other ROs (where relevant) | E.g. CAROs/ESMs/deputies
Internal service providers | E.g. IT support team, Print services, HR
External service providers | E.g. software supplier, hardware supplier, printers, specialist stationery suppliers, Royal Mail, IER Digital Service…
Police | E.g. local SPOC

## Evaluation
| What worked well | Objectives met? | Issues to be addressed | Key recommendations | To be completed by (date) | Responsible officer
Project planning
E.g. timeliness of delivery, adequacy of task allocation
Collaborative working (where relevant)
E.g. working with ERO, other ROs, CAROs (as appropriate) and elections staff at other local authorities
Adequacy of polling places/stations
E.g. in relation to location/accessibility/size/equipment, response to any concerns arising from evaluation of suitability of polling stations
Equipment and stationery
E.g. stock levels
Printers
E.g. quality, timescales, price, communication
Software performance
E.g. performance of software, identification of any changes required to ease processing, supplier’s response to any issues
Management of contractors
E.g. performance of contractors: communication, effectiveness of contracts, value for money
Recruitment and training (temporary and permanent)
E.g. was the training effective, were the staff efficient
Processing/handling of queries
E.g. adequacy of FAQs, complaints recording process
Resources
E.g. staffing levels, availability of resources
Security/integrity
E.g. any problems that arose, comments/feedback from SPOC
Verification and count arrangements
E.g. suitability of venue and layout
Electoral registration
E.g. success of public awareness work, enquiries from electors not registered
Postal voting
E.g. did all those who requested a postal vote receive one (including those overseas), any issues surrounding verification of personal identifiers
Voter Identification
E.g. volume of Voter Authority Certificates applied for and issued, enquiry handling both pre poll and on the day.
Candidates and agents
E.g. feedback from candidates and agents on process and provision of information
Communication
E.g. methods used for communicating information about the election and the voting process, did voters understand the process
Summary of feedback
E.g. feedback received from voters and other stakeholders, including verbal feedback or through a structured survey

## Test1 (hidden)
Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11 | Column12 | Column13 | Column14 | Column15 | Column16 | Column17 | Column18 | Column19 | Column20
a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b
c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c
a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b
c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c
a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b
c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c
a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b
c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c
a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b
c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c
a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b
c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c
a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b
c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c
a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b
c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c
a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b
c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c | c
a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a | a
b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b | b