## Front cover
RO Risk register
Local Government Elections in England, Combined Authority Mayoral elections, Police and Crime Commissioner elections in England and Wales.
Date:
Author:
Document version:
Reviews:
Name | Role | Date | Sign-off (ü)

## How to...
How to use this template
This risk register template provides some example risks and suggestions for mitigating them. In addition to the risks identified in the template, you should also identify any other risks, including ones specific to your local circumstances, and how you would mitigate those. This template also provides a template issues register to log any issues that arise and subsequent action taken.
Defining the level of impact and likelihood of risk
Inherent risk evaluation
How likely is it that the risk going to happen?
Unlikely = Likelihood of occurrence is relatively slim, less than 10% chance of occurrence
Possible = Quite possible that the risk could occur especially if control measures are inadequate, between 10% and 50% chance of occurrence
Probable = More likely to happen than not, greater than 50% chance of occurrence
What would the impact be if the risk was to crystallise?
Minor = Unlikely to have a permanent or significant effect
Moderate = Potential impact on performance and service delivery. May be adequately managed through existing processes
Significant = Severe impact on performance through a reduced ability to deliver.
The 3x3 matrix below can be used to calculate the overall risk score:
| IMPACT | 3 | 3 | 6 | 9
|  | Significant | (Significant & Unlikely) | (Significant & Possible) | (Significant & Probable)
|  | 2 | 2 | 4 | 6
|  | Moderate | (Moderate & Unlikely) | (Moderate & Possible) | (Moderate & Probable)
|  | 1 | 1 | 2 | 3
|  | Minor | (Minor & Unlikely) | (Minor & Possible) | (Minor & Probable)
|  |  | 1 - Unlikely | 2 - Possible | 3 - Probable
LIKELIHOOD
Residual risk evaluation
Once the appropriate action has been identified to address an individual risk, the action is given a score of 1 to 3 based on an assessment of how likely it is to be effective in reducing the risk (not all risks are capable of being reduced).
The risk owner will need to make an assessment as to whether the control measures are:
Good: Would score a 3, i.e. control measures are fully in place, agreed by line manager and form part of everyday activity
Average: Would score a 2, i.e. some controls in place but further actions to be planned and/or executed
Poor: Would score a 1, i.e. no control measures in place as yet, although actions may be planned
The initial (inherent) risk score is then divided by the score for the control action to give a residual risk score. This is the ultimate assessment of the scale of the risk and whether it is Red, Amber or Green.
Guidance
As an RO, you will need a risk register for delivering the election in your local authority area as Returning Officer. Our guidance for local Returning Officers and template risk register are also available on our website: www.electoralcommission.org.uk/i-am-a/electoral-administrator

## Risk register
Risk register
Number | Risk | Cause | Impact description | Likelihood | Impact | Inherent rating | Mitigation / current controls | Control score | Residual rating | Further action required | Lead Officer | Date of completion
PLANNING
| Failure to ensure proper plans in place | No comprehensive written project plan | Necessary actions not completed or completed late | 0 | 0 | 0 | Maintain and update project plan to ensure all necessary activities are planned for, and sufficient resources are available as and when required | 0 | #DIV/0!
|  | Poor planning assumptions | Missed deadlines |  |  |  | Ensure evaluation of previous electoral events has been integrated into the planning process
|  | Lack of understanding of the legislative requirements or any changes to legislation. | Potential breach of legislation |  |  |  | Ensure plans are in line with objectives and success measures, as well as Commission guidance (and, in the case of a regionally coordinated election, in line with any guidance or directions issued by the CARO, PARO or GLRO)
|  |  | Incorrect estimate of level of turnout |  |  |  | Ensure plans reflect a realistic estimate of the level of turnout, basing it, at a minimum, on the turnout at the last equivalent polls and take into account events that may increase turnout
|  | Failure to liaise with ERO or other Returning Officer(s) (as appropriate) | Lack of coordination and absence of consistent voter experience |  |  |  | Ensure liaison with relevant ERO/RO(s)/CARO/PARO/GLRO (as appropriate) to manage expectations and deadlines
Differing franchises at combined polls (Wales only)
| Electoral event called at short notice | By-election / local referendum to take place alongside or close to scheduled polls | Unable to deliver a successful unscheduled electoral event and detrimental impact on scheduled election | 0 | 0 | 0 | Ensure plans in place to be able to run a successful unscheduled electoral event, including at short notice | 0 | #DIV/0!
LOSS OF PREMISES
| Venues not available | Short notice of poll means that usual venues are unavailable | Staff working in unfamiliar venues Electors unsure of where to go to vote Inefficient count or postal vote opening processes due to layout changes | 0 | 0 | 0 | Book venues at earliest opportunity, making use of provisional bookings where possible Prepare lists of alternative venues, including making standby arrangements for use of portacabins, mobile vehicles, or marquees if necessary and appropriate | 0 | #DIV/0!
RO to work with other senior leaders across the council to negotiate where challenges arise and identify alternative venues across council buildings or partner organisations to use in emergencies
Ensure layout plants available and adaptable for changes in usual venues Ensure clear communication with stakeholders including electors, candidates and agents if usual venues are unavailable to identify new locations
| Loss of polling stations | Venue affected by flood, fire, vandalism, etc. | Voters unable to cast their vote | 0 | 0 | 0 | Prepare list of alternative venues, including making standby arrangements for use of portacabins/mobile vehicles if necessary | 0 | #DIV/0!
Brief Presiding Officers on possible emergency alternatives (e.g. setting up a temporary polling station in their car)
| Loss of postal vote issue/opening venue | Venue affected by flood, fire, vandalism, etc. | Delay in delivery of postal ballot packs If it affects the last opening session, potential delay to the verification and count | 0 | 0 | 0 |  | 0 | #DIV/0!
| Loss of verification and count venue | Venue affected by flood, fire, vandalism, etc. | Delay in completing the verification | 0 | 0 | 0 | Identify alternative venues | 0 | #DIV/0!
|  |  | Delay in counting |  |  |  | Have in place an emergency protocol that ensures the security of ballot papers
|  |  | Delay in declaration of result |  |  |  | Ensure staff are briefed on what to do in such circumstances
Have in place a process for notifying candidates and agents, the media and any other attendees of any changes to verification and count arrangements
| Loss of elections office | Office affected by power failure, flood, fire, vandalism, etc. | Unable to administer elections | 0 | 0 | 0 | Check council’s emergency plan for relocation and security arrangements, and identify alternative temporary accommodation | 0 | #DIV/0!
|  |  | Loss of data |  |  |  | Have in place a process to re-direct enquiries and visitors, including candidates and agents delivering their nomination papers
Have in place a plan for communicating to voters, candidates, agents and others any changes to your office location
Ensure daily back-up of data held off-site
FAILURE OF IT PROVISION
| Loss of IT capability | System or network failure | Unable to administer the election to the required deadlines | 0 | 0 | 0 | Perform daily back-ups and download documentation onto disc for secure storage off-site | 0 | #DIV/0!
|  | Power failure | Need to carry out processes manually |  |  |  | Ensure hard copies of data are available
|  | Cyber attack |  |  |  |  | Check with electoral registration/election management software supplier with regards to availability of duplicate system
IT provider to ensure adequate support throughout the period of the election and particularly on critical days
Check with IT provider with regards to corporate processes in place to prevent cyber attacks
Emergency generator provision by IT provider
| If you are also the ERO, failure of IER digital service or ERO Portal | Service outage | Unable to receive and process registration applications, absent vote applications, Voter Authority Certificate or Anonymous Elector's Document applications made online | 0 | 0 | 0 | Contingency plans for in place based on following guidance: https://www.electoralcommission.org.uk/running-electoral-registration-england/processing-applications-and-other-amendments-register-throughout-year/verification-applicants-identity/what-happens-if-ier-digital-service-unavailable Contingency plans for in place based on following guidance: https://www.electoralcommission.org.uk/running-electoral-registration-england/processing-applications-and-other-amendments-register-throughout-year/verification-applicants-identity/what-happens-if-ier-digital-service-unavailable, https://www.electoralcommission.org.uk/running-electoral-registration-wales/processing-applications-and-other-amendments-register-throughout-year/verification-applicants-identity/what-happens-if-ier-digital-service-unavailable Contingency plans for ERO Portal to be published once available. Contingency plans for ERO Portal to be published once available. | 0 | #DIV/0!
| Delay in postal vote opening session | Technical problems with scanners/ printers | Unable to verify postal vote identifiers electronically | 0 | 0 | 0 | Ensure scanners have been fully serviced and tested | 0 | #DIV/0!
|  |  | Integrity of poll brought into question |  |  |  | Identify alternative printers and scanners within the building and ensure necessary network connections are in place
|  |  | If it affects the last opening session, potential delay to the verification and count |  |  |  | Have sufficient scanning capacity so that the breakdown of one scanner would not delay a postal vote opening session
Draw up contingency plans for undertaking postal vote identifier verification manually ensuring that access to hard copies of postal vote application forms is available
COMMUNICATION
| Queries unable to reach electoral staff | Telecom/fax/IT failure | Voter confusion | 0 | 0 | 0 | Ensure dedicated line to election office, plus mobile numbers made available as back up | 0 | #DIV/0!
|  | Wrong advice given to voters | Voters unable to register or to vote |  |  |  | Seek out use of other fax machines within building to use if necessary |  | #DIV/0!
|  | Lack of voter information |  |  |  |  | IT provider to ensure adequate support throughout the period of the election and particularly on critical days |  | #DIV/0!
Emergency generator provision by IT provider
Ensure all outgoing information contains election office contact details
Provide frontline staff with FAQs
| Registration forms/postal vote/Voter Authority Certificate/Anonymous Elector's Document applications do not reach office before the deadlines | Telecom/fax/IT failure/digital service outage (if also the ERO) | Voter confusion | 0 | 0 | 0 | Ensure dedicated line to election office, plus mobile numbers made available as back up. Contingency plans in place. | 0 | #DIV/0!
|  | Wrong advice given to voters | Voters unable to register and vote |  |  |  | Seek out use of other fax machines within building to use if necessary
|  | Lack of voter information |  |  |  |  | IT provider to ensure adequate support throughout the period of the election and particularly on critical days
|  |  | Registered voters without acceptable photographic ID unable to vote |  |  |  | Emergency generator provision by IT provider
|  |  | Registered voters unable to apply for postal votes |  |  |  | Provide frontline staff with FAQs
Public awareness strategy to make provision for communication of key deadlines
| Large volume of Voter Authority Certificates and/or Anonymous Elector's Documents close to deadline. | Lots of publicity, particularly around deadlines. Public misunderstanding about all the different acceptable forms of photographic ID. | Pressure on ERO to determine and issue in time for central delivery. | 0 | 0 | 0 | Early communication with voters about the different types of acceptable photographic ID that can be used. Build capacity in the team to deal with any increase in volume of applications close to the deadline. Ensure system is in place to issue Temporary Voter Authority Certificates and Anonymous Elector's Documents. | 0 | #DIV/0!
| Large volume of absent vote applications close to deadline | Lots of publicity, particularly around deadlines. Public misunderstanding about the changes to the absent vote application process | Pressure on ERO to determine and issue in time for central delivery. | 0 | 0 | 0 | Build capacity in the team to deal with any increase in volume of applications close to the deadline. Ensure processes are in place to deal with the late issue of postal votes Communication with voters about the new requirements for absent vote applications | 0 | #DIV/0!
CONTRACTORS AND SUPPLIERS
| Inadequate materials to provide sufficient ballot papers or postal packs | Low stocks of material Election called at short notice | Unable to provide 100% of required ballot papers or postal packs | 0 | 0 | 0 | Early communication with suppliers around anticipated volumes and colours of products needed Clear communication of when final numbers will be confirmed | 0 | #DIV/0!
| Non/late delivery of poll cards/postal ballot packs | Missed printing deadlines or non-completion | Electors unaware of when/where to vote | 0 | 0 | 0 | Check out performance of potential suppliers with other clients and consider visiting premises of the selected contractor to inspect capacity, set up and processes | 0 | #DIV/0!
|  | Postal strike |  |  |  |  | Close liaison with contractor to identify potential problems in advance
Consider contingency arrangements to print products elsewhere in the event of non-completion
Ensure robust proofing procedures are in place and include quality checking mechanisms in contract or in any in-house arrangements prior to issue
Close liaison with account manager at Royal Mail
Consider alternative options for distribution e.g. by hand using in-house teams or by an alternative provider/carrier
Develop process for re-issue of lost/not received postal ballot packs during legislative time-frame
Consider alternative means of getting postal ballot packs back to the Returning Officer in time for close of poll (e.g., establishing postal vote collection points and promoting the ability for voters to hand in their completed postal ballots at polling stations in the voting area) Contact EC for advice in serious situations
| Poll cards/ballot papers/postal ballot packs do not contain correct information | Printing errors / lack of checking mechanisms | Voters do not receive the correct information and are unable to cast their vote/ their vote is not counted | 0 | 0 | 0 | Ensure robust proofing procedures are in place and that quality checks are carried out throughout the process (including checking live proofs and attending the issue of postal ballot papers) | 0 | #DIV/0!
Confirm ballot paper details, including checking proofs as appropriate before printing
Undertake checking of ballot papers once delivered to ensure they are correct, and where ballot papers are collected in advance of polling day by Presiding Officers, require them to check the sequential numbering of ballot papers on collection Contact EC for advice in serious situations
| Non-delivery of Voter Authority Certificates/ Anonymous Elector's Documents | Production or postal issues with central provider. | Voters without acceptable forms of photographic ID unable to vote. Pressure on ERO to issue large volume of Temporary Voter Authority Certificates or Anonymous Elector's Documents. | 0 | 0 | 0 | Ensure system of issuing Temporary Voter Authority Certificates and/or Anonymous Elector's Documents is in place. Contingency plans for ERO Portal to be published once available. | 0 | #DIV/0!
INTEGRITY ISSUES
| Possible electoral fraud not identified | Integrity issues not considered in planning process | Police investigations or legal challenges to the results of elections | 0 | 0 | 0 | Have mechanisms in place to assess the risk of electoral fraud in your area | 0 | #DIV/0!
Plans for managing the risk of electoral fraud in your area reflect any specific local risks and advice from local police SPOC
Develop your plans in collaboration with the local SPOC. Establish and maintain contact with your SPOC from the outset, with regular contact scheduled
Consider communicating approach to tackling fraud in advance of polling day to provide reassurance to voters and campaigners
| An individual applies to vote as someone else in the polling station | Electoral fraud | Integrity of the result is called into question | 0 | 0 | 0 | Voter is required to present photographic ID | 0 | #DIV/0!
Presiding Officers to ask statutory questions where appropriate and know what to do if they suspect electoral fraud
The voter can only be issued with a ballot paper if the statutory questions are answered satisfactorily and provides acceptable photographic ID.
Presiding Officer to hold police contact number
Prepare template for polling station staff for recording statements
| An individual uses someone elses postal vote | Electoral fraud | Integrity of the result is caled into question | 0 | 0 | 0 | Processes in place for verification of personal identifiers provided on the postal vote with those held on record. Processes in place for re-issuing postal votes. Liaison with local police spoc for any suspicions of fraud. | 0 | #DIV/0!
| A threat to candidate security | Incident at polling stations or other electoral events | Candidates unable to participate freely; integrity of poll called into question | 0 | 0 | 0 | Liaison with local police SPOC | 0 | #DIV/0!
Review of security arrangements and analysis of risks
Processes in place to maintain security at electoral events, including actions to be taken in case of disruptive behaviour
Inform attendees of entry requirements for the count, any other additional secrity measures in place and the standards of behaviour expected
| A threat to public safety | Public order incident | Delay/ postponement of poll | 0 | 0 | 0 | Liaison with local police SPOC | 0 | #DIV/0!
Review of security arrangements and analysis of risks
Police attendance at polling stations and the count according to level of risk identified
| Ballot papers interfered with | Security of election stationery is breached | Integrity of the poll is called into question | 0 | 0 | 0 | Ensure method of storage is such that you can be satisfied that you have taken all necessary steps to ensure that the ballot papers are kept securely | 0 | #DIV/0!
STAFFING
| Unable to appoint sufficient staff | Insufficient/non-provision of resources | Insufficient staff to cover processes | 0 | 0 | 0 | Early agreement on availability and release of local authority staff, drawing in any extra support from across the local authority as necessary | 0 | #DIV/0!
|  | Difficulty in recruiting suitable staff |  |  |  |  | Seek alternative sources of recruitment – e.g. community groups
|  | Difficulty or failure to appoint sufficient staff due to poll being called at short notice |  |  |  |  | Ensure staffing needs are analysed as early as possible both within the core team and for all other electoral processes including polling stations, postal voting and the count. Ensure that sufficient staff have been identified and allocated to all electoral processes, and that any previously used staff at previous elections are contacted as early as possible to confirm availability
Consider training additional staff as a contingency
| Loss of staff | Sickness | Insufficient number of staff to cover processes | 0 | 0 | 0 | Ensure all staff have contact details for the election office for use in the event that they can no longer attend | 0 | #DIV/0!
|  | Outbreak of pandemic or other contagious illness affecting large numbers of election staff |  |  |  |  | Ensure list of trained, reserve staff with contact numbers is in place
Provide appropriate training and guidance notes to staff who have been re-deployed and are carrying out unfamiliar tasks
Consult with local authority’s contingency planning unit
Have processes in place to minimise the risk of cross-infection, taking into consideration any advice provided by the Department of Health
| Insufficient support staff appointed | No detailed assessment of staffing requirements | Inability/difficulty in meeting deadlines | 0 | 0 | 0 | Map out staffing requirements based on robust planning assumptions at an early stage in planning process | 0 | #DIV/0!
|  |  | Mistakes by overworked staff, which could adversely affect voters |  |  |  | Consider need to appoint temporary support staff to assist the project team at different points of the proces
| Mistakes by inexperienced staff or by staff not fully aware of legislation /procedure | Inadequate/lack of training | Voters are unable to cast their vote | 0 | 0 | 0 | Training to be scheduled for all staff to ensure they are provided with the necessary information to be able to undertake their duties, including data protection considerations, what documents are acceptable photographic ID to use in a polling station, and how to handle postal votes returned by hand either to the polling station or the council offices in the run up to and on polling day. | 0 | #DIV/0!
Postal votes are incorrectly returned to polling stations or council offices and rejected
|  |  | Results called into question |  |  |  | Provide adequate resources such as guidance notes and polling station handbooks to relevant staff
Use of polling station inspectors to troubleshoot any issues identified on polling day
POLLING DAY
| Printed polling station registers incomplete or with errors | Lack of adequate checks | Not everyone who is entitled to vote is able to do so | 0 | 0 | 0 | Processes in place for checking polling station registers before and after being given to Presiding Officers to ensure that the printed registers include all eligible electors Mechanism in place for communicating amendments as a result of a clerical error | 0 | #DIV/0!
| Presiding Officer unable to gain access to polling station | Venue manager does not provide keys | Delay in opening the polling station | 0 | 0 | 0 | Presiding Officer to open up temporary polling station outside with guidance from the electoral services office, pending access being made available | 0 | #DIV/0!
|  | Vandalism, loss of venue etc. |  |  |  |  | Consider having a locksmith on call
Prepare list of alternative venues, including making standby arrangements for use of portacabins/ mobile vehicles if necessary
| Poor accessibility to the voting process, including for disabled voters | RO has not paid due regard to duty or guidance to enable disabled people to vote independently. | Not everyone who is entitled to vote is able to do so independently and in secret | 0 | 0 | 0 | RO has reviewed provision of accessibility equipment and arrangements in place in their polling stations in line with guidance and liaison with any relevant local groups. Accessiblity of polling stations is fully considered as part of the review of polling districts and polling places Accessibility issues to be highlighted in training sessions for polling station staff | 0 | #DIV/0!
|  | Polling station not set-up appropriately |  |  |  |  | Provide training for staff on good customer care and access issues
Give Presiding Officers instructions about installing any necessary accessibility alterations and equipment
|  | Staff not adequately trained in how to use equipment or customer service |  |  |  |  | Require Presiding Officers to set up the polling station with reference to the checklist in the polling station handbook
Ensure Presiding Officers and polling station inspectors carry out checks throughout polling day
| Incorrect processes followed for return of postal votes | Staff not adequately trained | Postal votes returned to polling stations are incorrectely accepted or rejected | 0 | 0 | 0 | Provide training for staff on new postal vote handling procedures Giving Presiding Officers clear instructions on what to do with returned postal votes, referring to the process in the polling station handbook Ensure polling station inspectors carry out checks on the process throughout the day | 0 | #DIV/0!
| Missing equipment | Equipment not properly prepared prior to poll | Delay in issuing ballot papers to electors | 0 | 0 | 0 | Use checklist for preparing sundries | 0 | #DIV/0!
Instruct Presiding Officer to check box and accompanying materials on receipt
Equip visiting officers with spare equipment/stationery
| Electoral registration problems | Errors on registers | Not everyone who is entitled to vote is able to do so | 0 | 0 | 0 | Liaison between ERO and RO and their respective staff to establish communication procedures for use on polling day | 0 | #DIV/0!
|  | Staff unaware of clerical errors procedure |  |  |  |  | Ensure helpline is equipped to deal with all polling day queries and the electoral services office is staffed throughout polling day to handle electoral registration queries
|  | Late determination of postal vote applications | Lats minute postal vote issues required up to close of poll |  |  |  | Adequate stocks of extra blank postal voting packs and staff available to issue postal votes to electors. Processes in place to ensure late deteremined postal vote applicants can still receive and return their postal vote. Communication lines open with ERO to obtain numbers of potential late determinations. Process in place for updating polling station registers and absent voting lists.
| Problems managing the voter ID process | Public lack of knowledge or understanding about the requirements. | Not everyone who is entitled to vote is able to do so | 0 | 0 | 0 | National and local public awareness raising, working with local groups to ensure acceptable types of photographic ID are well known. Flexible staffing used to help inform voters as they enter the polling station. | 0 | #DIV/0!
|  | Lack of staff understanding or confidence in the process and knowledge of the different types of acceptable forms of photographic ID | Loss of public confidence in the system |  |  |  | Voter ID is comprehensively covered in staff training. Polling station handbooks are provided for all staff. Notices and placemats are provided for all polling stations. Ensure helpline and Polling Station Inspectors details readily available to assist with any questions on the day.
| A threat to public safety | Problems with voter dissatisfaction or aggressive behaviour | Threatening behaviour towards staff | 0 | 0 | 0 | Provide guidance and training to front line staff, including FAQs to assist with giving answers to common queries | 0 | #DIV/0!
|  |  | Delay/ postponement of poll |  |  |  | Provide guidance on dealing with aggressive customers, drawing on resources developed by other council departments
Provide contact details for the police
| The public are unable to cast their votes | Polling station runs out of ballot papers | Results of election called into question | 0 | 0 | 0 | Allocation of 100% of ballot papers | 0 | #DIV/0!
Use of polling station inspectors to monitor and troubleshoot throughout polling day
THE VERIFICATION AND COUNT
| Unable to begin counting votes at projected start time | Inadequate planning | Delay in counting | 0 | 0 | 0 | Plans reflect measures to be taken to ensure counting of votes can begin at projected start time. e.g. transportation arrangements for ballot papers, verifying postal vote identifiers throughout polling day, robust planning for verification process | 0 | #DIV/0!
| Insufficient space at venue(s) | Inadequate planning | Lack of transparency and loss of confidence in the process | 0 | 0 | 0 | Plan layout of verification and count venue(s) in advance, allocating space to accommodate all those entitled to attend | 0 | #DIV/0!
| Delay of delivery of ballot boxes from the polling station to the verification venue/failure of ballot boxes to arrive from the polling station | Presiding Officer has difficulties getting from the polling station to the verification venue (e.g., becomes lost, severe weather, car breaks down, has an accident) | Delay in verification | 0 | 0 | 0 | Agree ballot box delivery routes from polling stations to verification location | 0 | #DIV/0!
Establish effective lines of communication between central control point and individual vehicles
Contact details of all Presiding Officers to be available at the verification venue
| Security of ballot papers | Inadequate planning |  | 0 | 0 | 0 | Liaise with police SPOC to discuss how to maintain the security of ballot papers at all stages of the election process | 0 | #DIV/0!
Brief candidates and agents on the arrangements to increase confidence in the process
| Failure of IT systems | Failure of power supply, loss of data, equipment failure | Delay in verification | 0 | 0 | 0 | Have contingency, manual arrangements in place for verification and count figures/calculations | 0 | #DIV/0!
|  |  | Delay in counting |  |  |  | Have IT support staff available at the verification and count venue
| Errors during verification of ballot paper accounts | Inadequate training | Delay to completion of verification and count | 0 | 0 | 0 | Develop clear, easy-to-use ballot paper accounts | 0 | #DIV/0!
|  |  | Inaccurate result |  |  |  | Ensure Presiding Officers are adequately trained to avoid errors in the completion of their ballot paper accounts
| Evacuation of verification and/or count centre | Emergency alarm activated (due to fire, etc.) | Delay to declaration of result | 0 | 0 | 0 | Have in place an emergency protocol for the verification/count | 0 | #DIV/0!
|  |  | Security of ballot papers compromised |  |  |  | Ensure that evacuation and re-entry procedures are developed so that any evacuation can be conducted in such a way as to ensure that the verification and count are not compromised i.e., ballot boxes and papers are secured or removed from premises
|  |  | Potential loss of ballot papers |  |  |  | Make an appropriate announcement at the start of the verification and count to communicate evacuation procedures
If re-entry is not possible, invoke contingency plan
| Discrepancy between the verification figure and the number of votes counted | Planning and administration not robust | Loss of confidence in the process | 0 | 0 | 0 | Prepare templates of all documents which will be completed at the verification and count to provide a clear audit trail. Ensure your plans include instructions based on the Commission's guidance for resolving or explaining discrepancies. | 0 | #DIV/0!
|  | Verification and count procedures not sufficiently thorough or effective | Inaccurate result
| Close results or a tie in votes | Equity of votes cast on polling day | Recounts required or lots to be drawn | 0 | 0 | 0 | Planning in place for process in the result of ties and templates in place to provide a clear audit trail in the result of a challenge to a close result | 0 | #DIV/0!
| Delay of delivery of ballot boxes from secure storage to count venue (if applicable) | Severe weather, traffic, accident, vehicle breakdown, driver(s) unavailable | Delay to the count and loss of confidence in the process | 0 | 0 | 0 | Agree alternative ballot box delivery routes to count location | 0 | #DIV/0!
Agree a process for replacing unavailable driver(s) at short notice, e.g. have replacement driver(s) on stand-by.
Establish effective lines of communication between central control point and the driver(s)
Contact details of driver(s) delivering ballot boxes to be available at the count
| Unable to communicate local totals to the CARO/PARO/GLRO (regionally coordinated elections only) | Faliure of communication mechansim for transmitting local totals | Delay to the count and loss of confidence in the process | 0 | 0 | 0 | Comply with the CARO/PARO/GLRO instructions/guidance on the timetable for verification and counting, and the method to be used for transmitting the information accurately and securely, including the result collation protocol Participate in any training and rehearsals of the result collation process carried out by the CARO/PARO/GLRO Ensure all relevant staff are briefed/trained on the result collation protocol and communication process Test all communication channels to ensure they are working before verification/counting begins | 0 | #DIV/0!
| Legal action against the RO | Election petition | Result of election brought into question | 0 | 0 | 0 | Maintain a clear audit trail of processes, including evidence of a project management approach and structured risk management process | 0 | #DIV/0!
DATA SECURITY
| Failure to put in place adequate data security arrangements | Inadequate security of personal data | Breach of legislation | 0 | 0 | 0 | Liaison with local authority data protection officer | 0 | #DIV/0!
|  |  | Reputational damage/risk of sanction from ICO |  |  |  | Ensure you are registered as a data controller independent to your council, and have appropriate privacy notices in place and visable.
Ensure your document retention policy is up-to-date, covers every document you process, and that you and your staff adhere to it.
Ensure that data protection is integral to any new or existing contracts or data-sharing agreements, with clear agreements on how data is to be transmitted, processed, stored and destroyed
Ensure you have procedures in place to detect, report and investigate any personal data breach
Ensure staff are aware of data security importance/requirements and that data protection is reflected in their training

## Issue register
Issue register
This issues register can be used to record any issues arising. The log should cover the nature of the issue, its source, the date it was raised and its potential impact. It should also include the proposed action to deal with the issue, as well as assigning clear ownership to the issue and establishing the date of its anticipated resolution.
An issue which has occurred is usually the result of an earlier risk which has now become reality, therefore it is vital to ensure that both the issues register and risk register are live documents and that they are reviewed and updated in conjunction.
Issue (already occurred) | Issue source (Where/Who raised) | Date issue arose | Potential impact (1-3) | Action | Issue owner | Target date for resolution (completion date in brackets) | Status – Open/ Closed