## Front cover
RO Risk register
Scottish local council elections
Date:
Author:
Document version:
Reviews:
Name | Role | Date | Sign-off (ü)

## How to...
How to use this template
This risk register template provides some example risks and suggestions for mitigating them. In addition to the risks identified in the template, you should also identify any other risks, including ones specific to your local circumstances, and how you would mitigate those. This template also provides a template issues register to log any issues that arise and subsequent action taken.
Defining the level of impact and likelihood of risk
Inherent risk evaluation
How likely is it that the risk going to happen?
· Unlikely – Likelihood of occurrence is relatively slim - <10% chance of occurrence
· Possible – Quite possible that the risk could occur especially if control measures are inadequate - 10% - 50% chance of occurrence
· Probable – More likely to happen than not - >50% chance of occurrence
What would the impact be if the risk was to crystallise?
· Minor – Unlikely to have a permanent or significant effect
· Moderate – Potential impact on performance and service delivery. May be adequately managed through existing processes
· Significant – Severe impact on performance through a reduced ability to deliver.
The 3x3 matrix below can be used to calculate the overall risk score:
| IMPACT | 3 | 3 | 6 | 9
|  | Significant | (Significant & Unlikely) | (Significant & Possible) | (Significant & Probable)
|  | 2 | 2 | 4 | 6
|  | Moderate | (Moderate & Unlikely) | (Moderate & Possible) | (Moderate & Probable)
|  | 1 | 1 | 2 | 3
|  | Minor | (Minor & Unlikely) | (Minor & Possible) | (Minor & Probable)
|  |  | 1 - Unlikely | 2 - Possible | 3 - Probable
LIKELIHOOD
Residual risk evaluation
Once the appropriate action has been identified to address an individual risk, the action is given a score of 1 to 3 based on an assessment of how likely it is to be effective in reducing the risk (not all risks are capable of being reduced).
The risk owner will need to make an assessment as to whether the control measures are:
· Good: Would score a 3, i.e. control measures are fully in place, agreed by line manager and form part of everyday activity
· Average: Would score a 2, i.e. some controls in place but further actions to be planned and/or executed
· Poor: Would score a 1, i.e. no control measures in place as yet, although actions may be planned
The initial (inherent) risk score is then divided by the score for the control action to give a residual risk score. This is the ultimate assessment of the scale of the risk and whether it is Red, Amber or Green.
Guidance
As an RO, you will need a risk register for delivering the election in your local authority area as Returning Officer. Our guidance for local Returning Officers and template risk register are also available on our website: www.electoralcommission.org.uk/i-am-a/electoral-administrator

## Risk register
Risk register
Number | Risk | Cause | Impact description | Likelihood | Impact | Inherent rating | Mitigation / current controls | Control score | Residual rating | Further action required | Lead Officer | Date of completion
PLANNING
| Failure to ensure proper plans in place | No comprehensive written project plan | Necessary actions not completed or completed late | 0 | 0 | 0 | Maintain and update project plan to ensure all necessary activities are planned for, and sufficient resources are available as and when required | 0 | #DIV/0!
|  | Poor planning assumptions | Missed deadlines |  |  |  | Ensure evaluation of previous electoral events has been integrated into the planning process
|  |  | Potential breach of legislation |  |  |  | Ensure plans are in line with objectives and success measures, as well as any guidance or directions issued by the Convener of the EMB and Commission guidance
|  |  | Incorrect estimate of level of turnout |  |  |  | Ensure plans reflect a realistic estimate of the level of turnout, basing it, at a minimum, on the turnout at the last equivalent polls and take into account events that may increase turnout
|  | Failure to liaise with ERO | Lack of coordination and absence of consistent voter experience |  |  |  | Ensure liaison with relevant ERO
| Electoral event called at short notice | By-election to take place alongside or close to scheduled polls | Unable to deliver a successful unscheduled electoral event and detrimental impact on scheduled election | 0 | 0 | 0 | Ensure plans in place to be able to run a successful unscheduled electoral event, including at short notice | 0 | #DIV/0!
LOSS OF PREMISES
| Loss of polling stations | Venue affected by flood, fire, vandalism, etc. | Voters unable to cast their vote | 0 | 0 | 0 | Prepare list of alternative venues, including making standby arrangements for use of portacabins/mobile vehicles if necessary Ensure there is a plan for communicating contingency arrangements with the electorate and candidates and that they can be rolled out at short notice. | 0 | #DIV/0!
Brief Presiding Officers on possible emergency alternatives (e.g. setting up a temporary polling station in their car)
Liaise with emergency planning teams and council's neighbourhood services to ensure contingency plans are in place in the event of flooding/fire.
| Loss of postal vote issue/ opening venue | Venue affected by flood, fire, vandalism, etc. | Delay in delivery of postal ballot packs | 0 | 0 | 0 | Identify alternative venues | 0 | #DIV/0!
|  |  | If it affects the last opening session, potential delay to the verification and count |  |  |  | Have an emergency protocol in place, and ensure staff are briefed on what to do in such circumstances
| Loss of verification and count venue | Venue affected by flood, fire, vandalism, etc. | Delay in completing the verification | 0 | 0 | 0 | Identify alternative venues | 0 | #DIV/0!
|  |  | Delay in counting |  |  |  | Have in place an emergency protocol that ensures the security of ballot papers
|  |  | Delay in declaration of result |  |  |  | Ensure staff are briefed on what to do in such circumstances
Have in place a process for notifying candidates and agents, the media and any other attendees of any changes to verification and count arrangements
| Loss of elections office | Office affected by power failure, flood, fire, vandalism, etc. | Unable to administer elections | 0 | 0 | 0 | Check council’s emergency plan for relocation and security arrangements, and identify alternative temporary accommodation | 0 | #DIV/0!
|  |  | Loss of data |  |  |  | Have in place a process to re-direct enquiries and visitors
Have in place a plan for communicating to voters, candidates, agents and others any changes to your office location
Ensure daily back-up of data held off-site
FAILURE OF IT PROVISION
| Loss of IT capability | System or network failure | Unable to administer the election to the required deadlines | 0 | 0 | 0 | Perform daily back-ups and download documentation onto disc for secure storage off-site | 0 | #DIV/0!
|  | Power failure | Need to carry out processes manually |  |  |  | Ensure hard copies of data are available
Check with electoral management software supplier with regards to availability of duplicate system
IT provider to ensure adequate support throughout the period of the election and particularly on critical days
Emergency generator provision by IT provider
| Failure of IER digital service - information from ERO | Service outage | ERO unable to receive and process registration applications made online - consequences for the administration of the poll | 0 | 0 | 0 | Plan in place for liaison with ERO and protocol for action to be taken ERO contingency plans in place based on following guidance: https://www.electoralcommission.org.uk/running-electoral-registration-scotland/processing-applications-and-other-amendments-register-throughout-year/verification-applicants-identity/what-happens-if-ier-digital-service-unavailable | 0 | #DIV/0!
| Delay in postal vote opening session | Technical problems with scanners/ printers | Unable to verify postal vote identifiers electronically | 0 | 0 | 0 | Ensure scanners have been fully serviced and tested | 0 | #DIV/0!
|  |  | Integrity of poll brought into question |  |  |  | Identify alternative printers and scanners within the building and ensure necessary network connections are in place
|  |  | If it affects the last opening session, potential delay to the verification and count |  |  |  | Have sufficient scanning capacity so that the breakdown of one scanner would not delay a postal vote opening session
Draw up contingency plans for undertaking postal vote identifier verification manually ensuring that access to hard copies of postal vote application forms is available
COMMUNICATION
| Queries unable to reach electoral staff | Telecom/fax/IT failure | Voter confusion | 0 | 0 | 0 | Ensure dedicated line to election office, plus mobile numbers made available as back up | 0 | #DIV/0!
|  | Wrong advice given to voters | Voters unable to register or to vote |  |  |  | Seek out use of other fax machines within building to use if necessary |  | #DIV/0!
|  | Lack of voter information |  |  |  |  | IT provider to ensure adequate support throughout the period of the election and particularly on critical days |  | #DIV/0!
Emergency generator provision by IT provider
Ensure all outgoing information contains election office contact details
Provide frontline staff with FAQs
CONTRACTORS AND SUPPLIERS
| Non/late delivery of poll cards/postal ballot packs | Missed printing deadlines or non-completion | Electors unaware of when/where to vote | 0 | 0 | 0 | Check out performance of potential suppliers with other clients and consider visiting premises of the selected contractor to inspect capacity, set up and processes | 0 | #DIV/0!
|  | Postal strike |  |  |  |  | Close liaison with contractor to identify potential problems in advance
Consider contingency arrangements to print products elsewhere in the event of non-completion
Ensure robust proofing procedures are in place and include quality checking mechanisms in contract or in any in-house arrangements prior to issue
Close liaison with account manager at Royal Mail
Consider alternative options for distribution e.g. by hand using in-house teams or by an alternative provider/carrier
Develop process for re-issue of lost/not received postal ballot packs during legislative timeframe
Consider alternative means of getting postal ballot packs back to the Returning Officer in time for close of poll (e.g., establishing postal vote collection points and promoting the ability for voters to hand in their completed postal ballots at polling stations in the voting area) Contact EC for advice in serious situations
| Poll cards/ballot papers/postal ballot packs do not contain correct information | Printing errors / lack of checking mechanisms | Voters do not receive the correct information and are unable to cast their vote/ their vote is not counted | 0 | 0 | 0 | Ensure robust proofing procedures are in place and that quality checks are carried out throughout the process (including checking live proofs and attending the issue of postal ballot papers) | 0 | #DIV/0!
Confirm ballot paper details, including checking proofs as appropriate before printing
Undertake checking of ballot papers once delivered to ensure they are correct, and where ballot papers are collected in advance of polling day by Presiding Officers, require them to check the sequential numbering of ballot papers on collection Contact EC for advice in serious situations
INTEGRITY ISSUES
| Possible electoral fraud not identified | Integrity issues not considered in planning process | Police investigations or legal challenges to the results of elections | 0 | 0 | 0 | Have mechanisms in place to assess the risk of electoral fraud in your area | 0 | #DIV/0!
Plans for managing the risk of electoral fraud in your area reflect any specific local risks and advice from local police SPOC
Develop your plans in collaboration with the local SPOC. Establish and maintain contact with your SPOC from the outset, with regular contact scheduled
Consider communicating approach to tackling fraud in advance of polling day to provide reassurance to voters and campaigners
| An individual votes as someone else | Electoral fraud | Integrity of the result is called into question | 0 | 0 | 0 | Processes in place for re-issuing postal votes, including identification requirements | 0 | #DIV/0!
Presiding Officers to ask statutory questions where appropriate and know what to do if they suspect electoral fraud, following any agreed protocol in cases where personation is suspected
Presiding Officer to hold police contact number
Prepare template for polling station staff for recording statements
| A threat to public safety | Public order incident | Delay/ postponement of poll | 0 | 0 | 0 | Liaison with local police SPOC | 0 | #DIV/0!
Review of security arrangements and analysis of risks
Police attendance at polling stations and the count according to level of risk identified
| Ballot papers interfered with | Security of election stationery is breached | Integrity of the poll is called into question | 0 | 0 | 0 | Ensure method of storage is such that you can be satisfied that you have taken all necessary steps to ensure that the ballot papers are kept securely | 0 | #DIV/0!
STAFFING
| Unable to appoint sufficient staff | Insufficient/non-provision of resources | Insufficient staff to cover processes | 0 | 0 | 0 | Early agreement on availability and release of local authority staff | 0 | #DIV/0!
|  | Difficulty in recruiting suitable staff |  |  |  |  | Seek alternative sources of recruitment – e.g. community groups
Ensure sufficient staff have been identified and allocated to all electoral processes
Consider training additional staff as a contingency
| Loss of staff | Sickness | Insufficient number of staff to cover processes | 0 | 0 | 0 | Ensure all staff have contact details for the election office for use in the event that they can no longer attend | 0 | #DIV/0!
|  | Outbreak of pandemic or other contagious illness affecting large numbers of election staff |  |  |  |  | Ensure list of trained, reserve staff with contact numbers is in place
Provide appropriate training and guidance notes to staff who have been re-deployed and are carrying out unfamiliar tasks
Consult with council's contingency planning unit
Have processes in place to minimise the risk of cross-infection, taking into consideration any advice provided by the relevant Government departments
| Insufficient support staff appointed | No detailed assessment of staffing requirements | Inability/difficulty in meeting deadlines | 0 | 0 | 0 | Map out staffing requirements based on robust planning assumptions at an early stage in project planning process | 0 | #DIV/0!
|  |  | Mistakes by overworked staff, which could adversely affect the voter |  |  |  | Consider need to appoint temporary support staff to assist the project team at different points of the process.
| Mistakes by inexperienced staff or by staff not fully aware of legislation /procedure | Inadequate/lack of training | Voters are unable to cast their vote | 0 | 0 | 0 | Training to be scheduled for all staff to ensure they are provided with the necessary information to be able to undertake their dutie, including data protection considerations | 0 | #DIV/0!
|  |  | Results called into question |  |  |  | Provide adequate resources such as guidance notes and polling station handbooks to relevant staff
Use of polling station inspectors to troubleshoot any issues identified on polling day
POLLING DAY
| Printed polling station registers incomplete or with errors | Lack of adequate checks | Not everyone who is entitled to vote is able to do so | 0 | 0 | 0 | Processes in place for checking polling station registers before and after being given to Presiding Officers to ensure that the printed registers include all eligible electors Liaison between ERO and RO and their respective staff to establish communication procedures for use on polling day | 0 | #DIV/0!
| Presiding Officer unable to gain access to polling station | Venue manager does not provide keys | Delay in opening the polling station | 0 | 0 | 0 | Presiding Officer to open up temporary polling station outside with guidance from the electoral services office, pending access being made available | 0 | #DIV/0!
|  | Vandalism, loss of venue etc. |  |  |  |  | Consider having a locksmith on call
Prepare list of alternative venues, including making standby arrangements for use of portacabins/ mobile vehicles if necessary
| Poor accessibility to the voting process, including for disabled voters | Polling station not set-up appropriately | Not everyone who is entitled to vote is able to do so | 0 | 0 | 0 | Accessiblity of polling stations to be fully considered as part of the review of polling districts and polling places Accessibility issues to be highlighted in training sessions for polling station staff | 0 | #DIV/0!
|  | Staff not adequately trained |  |  |  |  | Provide training for staff on good customer care and access issues
Give Presiding Officers instructions about installing any necessary accessibility alterations
Require Presiding Officers to set up the polling station with reference to the checklist in the polling station handbook
Ensure Presiding Officers and polling station inspectors carry out checks throughout polling day
| Missing equipment | Equipment not properly prepared prior to poll | Delay in issuing ballot papers to electors | 0 | 0 | 0 | Use checklist for preparing sundries | 0 | #DIV/0!
Instruct Presiding Officer to check box and accompanying materials on receipt
Equip visiting officers with spare equipment/stationery
| Electoral registration problems | Errors on registers | Not everyone who is entitled to vote is able to do so | 0 | 0 | 0 | Liaison between ERO and RO and their respective staff to establish communication procedures for use on polling day | 0 | #DIV/0!
|  | Staff unaware of clerical errors procedure |  |  |  |  | Ensure helpline is equipped to deal with all polling day queries
| A threat to public safety | Problems with voter dissatisfaction or aggressive behaviour | Threatening behaviour towards staff | 0 | 0 | 0 | Provide guidance and training to front line staff, including FAQs to assist with giving answers to common queries | 0 | #DIV/0!
|  |  | Delay/ postponement of poll |  |  |  | Provide guidance on dealing with aggressive customers, drawing on resources developed by other council departments
Provide contact details for the police
| The public are unable to cast their votes | Polling station runs out of ballot papers | Results of election called into question | 0 | 0 | 0 | Allocation of 100% of ballot papers | 0 | #DIV/0!
Use of polling station inspectors to monitor and troubleshoot throughout polling day
THE VERIFICATION AND COUNT
| Unable to begin counting votes at projected start time | Inadequate planning | Delay in counting | 0 | 0 | 0 | Plans reflect measures to be taken to ensure counting of votes can begin at projected start time. e.g. transportation arrangements for ballot papers, verifying postal vote identifiers throughout polling day, robust planning for verification process | 0 | #DIV/0!
| Insufficient space at venue | Inadequate planning | Lack of transparency and loss of confidence in the process | 0 | 0 | 0 | Plan layout of count venue in advance, allocating space to accommodate all those entitled to attend | 0 | #DIV/0!
| Delay of delivery of ballot boxes from the polling station to the verification venue/failure of ballot boxes to arrive from the polling station | Presiding Officer has difficulties getting from the polling station to the verification venue (e.g., becomes lost, severe weather, car breaks down, has an accident) | Delay in verification | 0 | 0 | 0 | Agree ballot box delivery routes from polling stations to verification location | 0 | #DIV/0!
Establish effective lines of communication between central control point and individual vehicles
Contact details of all Presiding Officers to be available at the verification venue
| Security of ballot papers | Inadequate planning |  | 0 | 0 | 0 | Liaise with police SPOC to discuss how to maintain the security of ballot papers at all stages of the election process | 0 | #DIV/0!
Brief candidates and agents on the arrangements to increase confidence in the process
| Failure of IT systems, including issues relating to the electronic counting system | Failure of power supply, loss of data, equipment failure, technical issues with the system | Delay in verification | 0 | 0 | 0 | Have contingency arrangements in place for verification and count | 0 | #DIV/0!
|  |  | Delay in counting Delay in declaring the result |  |  |  | Have IT support staff available at the verification and count venue Ensure adequate power supply and back-up generation available at the count centre Check no planned works to the electricity supply on the day of the count Maintain a clear audit trail of processes, including evidence of a project management approach and structured risk management process
| Errors during verification of ballot paper accounts | Inadequate training | Delay to completion of verification and count | 0 | 0 | 0 | Develop clear, easy-to-use ballot paper accounts | 0 | #DIV/0!
|  |  | Inaccurate result |  |  |  | Ensure Presiding Officers are adequately trained to avoid errors in the completion of their ballot paper accounts
| Evacuation of verification and/or count centre | Emergency alarm activated (due to fire, etc.) | Delay to declaration of result | 0 | 0 | 0 | Have in place an emergency protocol for the verification/count | 0 | #DIV/0!
|  |  | Security of ballot papers compromised |  |  |  | Ensure that evacuation and re-entry procedures are developed so that any evacuation can be conducted in such a way as to ensure that the verification and count are not compromised i.e., ballot boxes and papers are secured or removed from premises
|  |  | Potential loss of ballot papers |  |  |  | Make an appropriate announcement at the start of the verification and count to communicate evacuation procedures
If re-entry is not possible, invoke contingency plan
| Discrepancy between the verification figure and the number of votes counted | Planning and administration not robust | Loss of confidence in the process | 0 | 0 | 0 | Ensure your plans include instructions based on the Commission's guidance for resolving or explaining discrepancies. | 0 | #DIV/0!
|  | Verification and count procedures not sufficiently thorough or effective | Inaccurate result
| Delay of delivery of ballot boxes from secure storage to count venue (if applicable) | Severe weather, traffic, accident, vehicle breakdown, driver(s) unavailable | Delay to the count and loss of confidence in the process | 0 | 0 | 0 | Agree alternative ballot box delivery routes to count location | 0 | #DIV/0!
Agree a process for replacing unavailable driver(s) at short notice, e.g. have replacement driver(s) on stand-by.
Establish effective lines of communication between central control point and the driver(s)
Contact details of driver(s) delivering ballot boxes to be available at the count
| Legal action against the RO | Election petition | Result of election brought into question | 0 | 0 | 0 | Maintain a clear audit trail of processes, including evidence of a project management approach and structured risk management process | 0 | #DIV/0!
DATA SECURITY
| Failure to put in place adequate data security arrangements | Inadequate security of personal data | Breach of legislation | 0 | 0 | 0 | Liaison with data protection officer | 0 | #DIV/0!
|  |  | Reputational damage/risk of sanction from ICO |  |  |  | Ensure you are registered as a data controller independent, and have appropriate privacy notices in place and visable.
Ensure your document retention policy is up-to-date, covers every document you process, and that you and your staff adhere to it.
Ensure that data protection is integral to any new or existing contracts or data-sharing agreements, with clear agreements on how data is to be transmitted, processed, stored and destroyed
Ensure you have procedures in place to detect, report and investigate any personal data breach
Ensure staff are aware of data security importance/requirements and that data protection is reflected in their training

## Issue register
Issue register
This issues register can be used to record any issues arising. The log should cover the nature of the issue, its source, the date it was raised and its potential impact. It should also include the proposed action to deal with the issue, as well as assigning clear ownership to the issue and establishing the date of its anticipated resolution.
An issue which has occurred is usually the result of an earlier risk which has now become reality, therefore it is vital to ensure that both the issues register and risk register are live documents and that they are reviewed and updated in conjunction.
Issue (already occurred) | Issue source (Where/Who raised) | Date issue arose | Potential impact (1-3) | Action | Issue owner | Target date for resolution (completion date in brackets) | Status – Open/ Closed