## Front cover
Combined Authority and Combined County Authority Returning Officer risk register
Combined Authority and Combined County Authority Mayoral elections
Date:
Author:
Document version:
Reviews:
Name | Role | Date | Sign-off (ü)

## How to...
How to use this template
This risk register template provides some example risks and suggestions for mitigating them. In addition to the risks identified in the template, you should also identify any other risks, including ones specific to your local circumstances, and how you would mitigate those. This template also provides a template issues register to log any issues that arise and subsequent action taken.
Defining the level of impact and likelihood of risk
Inherent risk evaluation
How likely is it that the risk is going to happen?
· Unlikely – Likelihood of occurrence is relatively slim - <10% chance of occurrence
· Possible – Quite possible that the risk could occur especially if control measures are inadequate - 10% - 50% chance of occurrence
· Probable – More likely to happen than not - >50% chance of occurrence
What would the impact be if the risk was to crystallise?
· Minor – Unlikely to have a permanent or significant effect
· Moderate – Potential impact on performance and service delivery. May be adequately managed through existing processes
· Significant – Severe impact on performance through a reduced ability to deliver.
The 3x3 matrix below can be used to calculate the overall risk score:
| IMPACT | 3 | 3 | 6 | 9
|  | Significant | (Significant & Unlikely) | (Significant & Possible) | (Significant & Probable)
|  | 2 | 2 | 4 | 6
|  | Moderate | (Moderate & Unlikely) | (Moderate & Possible) | (Moderate & Probable)
|  | 1 | 1 | 2 | 3
|  | Minor | (Minor & Unlikely) | (Minor & Possible) | (Minor & Probable)
|  |  | 1 - Unlikely | 2 - Possible | 3 - Probable
LIKELIHOOD
Residual risk evaluation
Once the appropriate action has been identified to address an individual risk, the action is given a score of 1 to 3 based on an assessment of how likely it is to be effective in reducing the risk (not all risks are capable of being reduced).
The risk owner will need to make an assessment as to whether the control measures are:
· Good: Would score a 3, i.e. control measures are fully in place, agreed by line manager and form part of everyday activity
· Average: Would score a 2, i.e. some controls in place but further actions to be planned and/or executed
· Poor: Would score a 1, i.e. no control measures in place as yet, although actions may be planned
The initial (inherent) risk score is then divided by the score for the control action to give a residual risk score. This is the ultimate assessment of the scale of the risk and whether it is Red, Amber or Green.
Guidance
The following risk register has been produced to support both Combined Authority Returning Officers (CAROS) in planning for and delivering a combined authority mayoral election and Combined County Authority Returning Officers (CCAROs) in planning for and delivering a combined county authority mayoral election in England. For the purpose of combined county authority mayoral elections, references in this guidance to combined authorities should be read as references to combined county authorities.
Further detailed guidance for CARO/CCAROs on planning for a combined authority mayoral election can be found on our website: www.electoralcommission.org.uk/i-am-a/electoral-administrator. The CARO/CCARO guidance should be read in conjunction with guidance produced for Returning Officers administering local government elections in England and Wales, which is also available on our website: www.electoralcommission.org.uk/i-am-a/electoral-administrator.
If you are also a local RO, you will need a risk register for delivering the election in your local authority area as Returning Officer. Our guidance for local Returning Officers and template risk register are also available on our website.

## Risk register
Risk register
Number | Risk | Cause | Impact description | Likelihood | Impact | Inherent rating | Mitigation / current controls | Control score | Residual rating | Further action required | Lead Officer | Date of completion
PLANNING
| Failure to ensure proper plans in place | No comprehensive written project plan | Necessary actions not completed or completed late | 0 | 0 | 0 | Maintain and update project plan to ensure all necessary activities are planned for, and sufficient resources are available as and when required | 0 | #DIV/0!
|  | Poor planning assumptions | Missed deadlines |  |  |  | Ensure evaluation of previous electoral events (particularly those with a regional or sub regional coordination aspect) and your experience of managing any previous polls have been integrated into the planning process (including taking into account experiences from other areas)
|  |  | Potential breach of legislation |  |  |  | Ensure plans are in line with objectives and success measures
|  |  | Incorrect estimate of level of turnout |  |  |  | Ensure that plans from local ROs reflect a realistic estimate of the level of turnout, basing it, at a minimum, on the turnout at the last equivalent polls and taking into account events that may increase turnout
| Failure to ensure ROs have proper plans in place | Monitoring strategy not in place and /or not implemented | Necessary actions not completed or completed late | 0 | 0 | 0 | Plan in place for monitoring local RO performance with support from EC | 0 | #DIV/0!
|  | Inadequate monitoring strategy | Errors or inconsistencies in administration of election |  |  |  | Monitoring properly resourced and carried out in a timely manner
|  | Poor communication with ROs | Result called into question |  |  |  | Local RO communication strategy in place
|  |  | Missed deadlines |  |  |  | Plans in place for delivery of training / briefings to Local ROs and their staff
|  |  | Potential breach of legislation |  |  |  | Reaching consensus with local ROs as to outcomes and documenting decisions reached, issuing guidance where necessary and directions where appropriate
LOSS OF PREMISES
| Loss of count venue (if counting centrally) / result calculation venue | Venue affected by flood, fire, vandalism, etc. | Delay in completing the verification | 0 | 0 | 0 | Identify alternative venues | 0 | #DIV/0!
|  |  | Delay in counting |  |  |  | Have in place an emergency protocol and ensure that local ROs have an emergency protocol that ensures the security of ballot papers
Ensure local ROs are aware of contingency arrangements and are briefed on what to do if primary result collation venue is lost
|  |  | Delay in declaration of result |  |  |  | Ensure staff are briefed on what to do in such circumstances
Have in place a process for notifying candidates and agents, the media and any other attendees of any changes to count arrangements or the result collation arrangements
| Loss of elections office | Office affected by power failure, flood, fire, vandalism, etc. | Unable to administer elections | 0 | 0 | 0 | Check council’s emergency plan for relocation and security arrangements, and identify alternative temporary accommodation | 0 | #DIV/0!
|  |  | Loss of data |  |  |  | Have in place a process to re-direct enquiries and visitors
Ensure daily back-up of data held off-site
FAILURE OF IT PROVISION
| Loss of IT capability | System or network failure | Unable to administer the election to the required deadlines | 0 | 0 | 0 | Perform daily back-ups and download documentation onto disc for secure storage off-site | 0 | #DIV/0!
|  | Power failure | Need to carry out processes manually |  |  |  | Ensure hard copies of data are available
IT provider to ensure adequate support throughout the period of the election and particularly on critical days
Emergency generator provision by IT provider
COMMUNICATION
| CARO/CCARO guidance / directions not received or not followed by local ROs | Poor communication strategy Local RO error Ineffective monitoring of local ROs - issues not identified and / or addressed IT failure | Errors or inconsistencies in administration of election | 0 | 0 | 0 | Ensure clear plan in place for communication with local ROs, including early communication of any requirements, guidance or directions. | 0 | #DIV/0!
Monitoring procedures in place to identify and take action in response to inadequate performance by local ROs
|  |  | Result called into question |  |  |  | Processes in place to check local ROs are complying with agreed outcomes, guidance and directions
Plans in place for delivery of training / briefings to local ROs and their staff
Alternative communication plans in place (e.g. telephone cascade) in event of power or IT failure
| Queries from local ROs unable to reach CARO/CCARO or their staff | Telecom / IT failure | ROs unable to obtain advice and guidance from CARO/CCARO | 0 | 0 | 0 | Ensure dedicated line to election office, plus mobile numbers made available as back up. Ensure out of hours emergency contact details are provided to local ROs . | 0 | #DIV/0!
|  | Errors or omissions in provision of contact details | Local ROs unable to refer external enquiries to CARO/CCARO |  |  |  | Ensure result collation protocol contains full contact details and back-up numbers to be used during the verification and count process. Seek out use of other communication methods within venue (e.g. fax machines) to use if necessary. IT provider to ensure support throughout election period and particularly on critical days. Emergency generator provided by IT provider. Ensure all outgoing information contains election office contact details
| Queries unable to reach electoral staff | Telecom/IT failure | Voter / candidate confusion | 0 | 0 | 0 | Ensure dedicated line to election office, plus mobile numbers made available as back up | 0 | #DIV/0!
|  | Wrong advice given to voters / candidates | Voters unable to register or to vote |  |  |  | Seek out use of other methods of communication (e.g. fax machines) within building to use if necessary |  | #DIV/0!
|  | Lack of voter / candidate information | Candidates unable to stand for election |  |  |  | IT provider to ensure adequate support throughout the period of the election and particularly on critical days |  | #DIV/0!
Emergency generator provision by IT provider
Ensure all outgoing information contains election office contact details
Provide frontline staff with FAQs
NOMINATIONS AND CANDIDATE ADDRESSES
| Errors or omissions in statement of persons nominated | Transcription mistake | Inaccurate information published about candidates | 0 | 0 | 0 | Plans in place for delivery of briefings to candidates and agents | 0 | #DIV/0!
|  | Candidate / agent errors in completing the forms | Incorrect information on the ballot papers |  |  |  | Provision of nomination packs and clear guidance on completion of forms
Process in place for informal checking of nominations
Voter confusion
Process in place for checking the accuracy of the statement of persons nominated before publication
| Loss of nomination papers | Inadequate processes in place for filing and storing paperwork | Candidates not able to participate | 0 | 0 | 0 | Plan in place for managing combined authority mayoral nominations Effective and secure storage arrangements in place | 0 | #DIV/0!
|  | Unable to access building or damage to building e.g. by fire , flood | Security / integrity of the election called into question |  |  |  | Contingency arrangements in place for access to back-up copies in event of inability to access building / loss of building
| Loss of access to electoral registers | Loss of access to elections office / loss of building | Unable to check subscribers | 0 | 0 | 0 | Contingency arrangements in place, agreed with EROs, for obtaining access to electoral registers in event of inability to access building / loss of building |  | #DIV/0!
|  | IT failure | Unable to accept candidate nominations |  |  |  |  | 0
| Requirement for content / submission of election addresses not complied with Failure or error in printing of booklets | Errors by candidate / agents in preparing and submitting addresses | Candidate addresses not accepted for publication - lack of candidate information for voters | 0 | 0 | 0 | Plans in place for delivery of briefings for candidates and agents Contingency plans in place | 0 | #DIV/0!
|  | Poor planning process for receiving, checking and submitting candidates addresses |  |  |  |  | Nominations packs issued explaining process for submission and requirements relating to the content of addresses
|  | Unclear communication / lack of communication with candidates/ agents about requirements |  |  |  |  | Timetable for submission of candidate addresses is established and communicated at an early stage to candidates and agents
|  | Errors by CARO/CCARO in checking and approving election addresses |  |  |  |  | Process in place for informal checking of addresses CARO/CCARO familiar with the legal requirements of candidates addresses and the Commission's guidance. Process in place for robust proof checking of the booklet.
CONTRACTORS AND SUPPLIERS
| Non/late delivery of poll cards/postal ballot packs | Missed printing deadlines or non-completion | Electors unaware of when/where to vote | 0 | 0 | 0 | Ensure local ROs have adequate arrangements in place with contractors, including contingency arrangements | 0 | #DIV/0!
|  | Printing errors | Voters unable to cast their vote |  |  |  | Ensure local ROs have robust proofing procedures in place and quality checking mechanisms
|  | Postal strike |  |  |  |  | Ensure local ROs have close liaison with account manager at Royal Mail
Ensure local ROs make appropriate provision where postal votes are sent overseas (including appropriate postage)
Ensure local ROs consider alternative options for distribution e.g. by hand using in-house teams or by an alternative provider/carrier
Ensure local ROs consider alternative means of getting postal ballot packs back in time for close of poll (e.g., establishing postal vote collection points and promoting the ability for voters to hand in their completed postal ballots at polling stations in the voting area)
| Poll cards/ballot papers/postal ballot packs do not contain correct information | Printing errors / lack of checking mechanisms | Voters do not receive the correct information and are unable to cast their vote/ their vote is not counted | 0 | 0 | 0 | Ensure local ROs have robust proofing procedures in place and that quality checks are carried out throughout the process (including the checking of live proofs and attendance at the issue of postal votes) | 0 | #DIV/0!
INTEGRITY ISSUES
| Possible electoral fraud not identified | Integrity issues not considered in planning process | Police investigations or legal challenges to the results of elections | 0 | 0 | 0 | Have mechanisms in place to assess the risk of electoral fraud in the combined authority area Invite the police to attend any briefings with candidates and agents and ensure you and local ROs liaise closely with the SPOCs | 0 | #DIV/0!
Integrity plan in place, plus plans for managing the risk of electoral fraud in individual local authority areas within the combined authority to reflect any specific local risks
Ensure candidates and campaigners are aware of the Code of conduct for campaigners
Consider communicating approach to tackling fraud in advance of polling day to provide reassurance to voters and campaigners
| A threat to public safety | Public order incident | Delay/ postponement of poll | 0 | 0 | 0 | Liaison with police SPOCs in combined authority area | 0 | #DIV/0!
Regular updates from local ROs on any local integrity issues identified / feedback from local SPOC
|  |  | Delay / postponement of calculation of result |  |  |  | Review of security arrangements and analysis of risks
Police attendance at the result calculation according to level of risk identified
| Ballot papers interfered with | Security of election stationery is breached | Integrity of the poll is called into question | 0 | 0 | 0 | Ensure local ROs' methods of storage are such that you can be satisfied that they have taken all necessary steps to ensure that the ballot papers are kept securely. | 0 | #DIV/0!
STAFFING
| Unable to appoint sufficient staff | Insufficient/non-provision of resources | Insufficient staff to cover processes | 0 | 0 | 0 | Early agreement on availability and release of combined authority staff and, if appropriate, local authority staff | 0 | #DIV/0!
Difficulty in recruiting suitable staff
Ensure sufficient staff have been identified and allocated to all electoral processes
Consider training additional staff as a contingency
| Loss of staff | Sickness | Insufficient number of staff to cover processes | 0 | 0 | 0 | Ensure all staff have contact details for the election office for use in the event that they can no longer attend | 0 | #DIV/0!
|  | Outbreak of pandemic or other contagious illness affecting large numbers of election staff |  |  |  |  | Ensure list of trained, reserve staff with contact numbers is in place
Provide appropriate training and guidance notes to staff who have been re-deployed and are carrying out unfamiliar tasks
Consult with combined authority’s and, if appropriate, the local authority's contingency planning unit
Have processes in place to minimise the risk of cross-infection, taking into consideration any advice provided by the Department of Health
| Insufficient support staff appointed | No detailed assessment of staffing requirements | Inability/difficulty in meeting deadlines | 0 | 0 | 0 | Map out staffing requirements at an early stage in project planning process. | 0 | #DIV/0!
|  |  | Mistakes by overworked staff, which could adversely affect the voter |  |  |  | Consider need to appoint temporary support staff to assist the project team at different points of the process.
| Mistakes by inexperienced staff or by staff not fully aware of legislation /procedure | Inadequate/lack of training | Voters are unable to cast their vote | 0 | 0 | 0 | Project team is sufficiently resourced with appropriate levels of skilled / experienced staff | 0 | #DIV/0!
|  |  | Results called into question |  |  |  | Plans in place to deliver training to the project team as required
Project management of planning, preparation and delivery of the election by CARO/CCARO project team
Training to be scheduled for all staff to ensure they are provided with the necessary information to be able to undertake their duties, including data protection considerations
Clear and timely communication to local ROs of all information, guidance, directions, procedures, plans and protocols
|  |  | Candidate unable to stand for election |  |  |  | Monitor local ROs' planning and preparations and intervene where necessary
POLLING DAY
| A threat to public safety | Problems with voter dissatisfaction or aggressive behaviour | Threatening behaviour towards staff | 0 | 0 | 0 | Provide guidance and training to front line staff, including FAQs to assist with giving answers to common queries | 0 | #DIV/0!
|  |  | Delay/ postponement of poll |  |  |  | Ensure local ROs have in place processes for dealing with aggressive behaviour
Provide contact details for the police
| The public are unable to cast their votes | Polling station runs out of ballot papers | Results of election called into question | 0 | 0 | 0 | Require local ROs to allocate of 100% of ballot papers | 0 | #DIV/0!
Require local ROs to use sufficient polling station inspectors to monitor and troubleshoot throughout polling day
THE RESULT CALCULATION
| Insufficient space at venue(s) | Inadequate planning | Lack of transparency and loss of confidence in the process | 0 | 0 | 0 | Plan layout in advance, allocating space to accommodate all those entitled to attend | 0 | #DIV/0!
| Failure of IT systems | Failure of power supply, loss of data, equipment failure | Delay in result collation | 0 | 0 | 0 | Have contingency, manual arrangements in place | 0 | #DIV/0!
Have IT support staff available at the venue
| Failure of count results collation system | Failure of power supply, loss of data, equipment failure | Delay in result collation | 0 | 0 | 0 | Ensure result collation protocol contains full contact details and back-up numbers to be used during the verification and count process. Have contingency, manual arrangements in place Seek out use of other methods of communication within venue to use if necessary. IT provider to ensure support throughout election period and particularly on critical days | 0 | #DIV/0!
| Evacuation of venue | Emergency alarm activated (due to fire, etc.) | Delay to declaration of result | 0 | 0 | 0 | Have in place an emergency protocol for the result collation, to include communicating with local ROs, and specifying what they should do in the event of a delay or postponement of the result collation process | 0 | #DIV/0!
|  |  | Security of election paperwork compromised |  |  |  | Ensure that evacuation and re-entry procedures are developed so that any evacuation can be conducted in such a way as to ensure that the result calculation are not compromised i.e. IT equipment and paperwork are or removed from premises
|  |  | Potential loss of election paperwork |  |  |  | Make an appropriate announcement at the start of the process to communicate evacuation procedures
If re-entry is not possible, invoke contingency plan and communicate what is happening to local ROs, candidates, agents the media and other attendees
| Local discrepancy between the verification figure and the number of votes counted | Planning and administration not robust | Loss of confidence in the process | 0 | 0 | 0 | Monitor local ROs' plans for verification and counting and take follow-up action if necessary, or set a verification and count methodology for local ROs to follow Ensure local verification and count processes are capable of providing a clear audit trail. | 0 | #DIV/0!
|  | Verification and count procedures not sufficiently thorough or effective | Inaccurate result
|  | Result collation protocol not sufficiently thorough or effective |  |  |  |  | Ensure result collation protocol includes steps for CARO/CCARO to review verification and count figures before they are confirmed and made public
| Problems or delays with the transmission of verification or count totals from local ROs to CARO/CCARO | Technical problems | Delay in result calculation | 0 | 0 | 0 | Clear and timely communication of process and timetable for verification, counting and result collation | 0 | #DIV/0!
|  | Verification and counting not commenced in accordance with agreements, guidance or direction from CARO/CCARO |  |  |  |  | Ensure local ROs and their staff are briefed / trained on the result collation protocol and communication process
Carry out a rehearsal of the result collation process involving local ROs and their staff
Carry out regular progress checks with local ROs during the verification and count process
Test all communication channels are working before verification / counting begins
| Errors in the transmission of local totals from ROs | RO / staff errors | Inaccurate result | 0 | 0 | 0 | Ensure result collation protocol enables accurate and secure transmission of information | 0 | #DIV/0!
|  | CARO/CCARO / staff errors | Delay in result calculation |  |  |  | Ensure local ROs and staff working on the transmission of information have undertaken training and taken part in the rehearsal(s) of the process
|  |  | Result called into question |  |  |  | Carry out a test notification in advance
Build in accuracy checks to result collation protocol
AFTER THE DECLARATION OF THE RESULT
| Legal action against the CARO/CCARO | Election petition | Result of election brought into question | 0 | 0 | 0 | Maintain a clear audit trail of processes, communications and information sent to and received from local ROs, including evidence of a project management approach and structured risk management process | 0 | #DIV/0!
DATA SECURITY
| Failure to put in place adequate data security arrangements | Inadequate security of personal data | Breach of legislation | 0 | 0 | 0 | Liaison with local authority data protection officer
|  |  | Reputational damage/risk of sanction from ICO |  |  |  | Ensure you are registered as a data controller independent to your council, and have appropriate privacy notices in place and visible
Ensure your document retention policy is up-to-date, covers every document you process, and that you and your staff adhere to it
Ensure that data protection is integral to any new or existing contracts or data-sharing agreements, with clear agreements on how data is to be transmitted, processed, stored and destroyed
Ensure you have procedures in place to detect, report and investigate any personal data breach
Ensure staff are aware of data security importance/requirements and that data protection is reflected in their training

## Issue register
Issue register
This issues register can be used to record any issues arising. The log should cover the nature of the issue, its source, the date it was raised and its potential impact. It should also include the proposed action to deal with the issue, as well as assigning clear ownership to the issue and establishing the date of its anticipated resolution.
An issue which has occurred is usually the result of an earlier risk which has now become reality, therefore it is vital to ensure that both the issues register and risk register are live documents and that they are reviewed and updated in conjunction.
Issue (already occurred) | Issue source (Where/Who raised) | Date issue arose | Potential impact (1-3) | Action | Issue owner | Target date for resolution (completion date in brackets) | Status – Open/ Closed