## Front cover
Electoral registration activity plan
Date:
Author:
Document version:
Reviews
Name | Role | Date | Sign-off (ü)

## How to...
Using this template
This template project plan is designed to support Electoral Registration Officers in planning for and delivering electoral registration. The template includes a number of example deliverables and tasks as set out in our guidance on Your Registration Plan to demonstrate how the template can be used. However, this is not designed as an exhaustive list and how you populate this plan will be dependent on your processes and the profile of your area. Your project plan should capture all of the work that you will need to undertake in planning for and delivering electoral registration activity, including how you will implement the actions identified in your local public engagement strategy.
Guidance on delivering electoral registration activity can be found on the Commission’s website at https://www.electoralcommission.org.uk/our-guidance/electoral-administrator
Objectives and success measures
Before compiling a detailed list of deliverables and tasks, the objectives of the project need to be established, i.e., what you want to achieve, and what success will look like. As part of your ongoing monitoring and evaluation, you should assess whether the stated objectives are being met, updating your plans and processes as necessary. The template provides some example objectives and suggestions for tools for measuring success. In addition, you should identify any other objectives and success measures, including ones specific to your local circumstances.
Dependencies and contact details
The delivery of electoral registration is dependent on a number of internal and external service providers. This tab should be populated with the names and contact details of your electoral registration project board and any other internal and external service providers. It also includes a template schedule to record meetings, plus space to document any actions arising from these meetings.
Resource requirements
This tab can be used to identify and set out what resources are required to deliver the plan.
Deliverables and tasks
Once the objectives have been identified, individual tasks can be planned for and owners allocated to these. This tab identifies a number of example deliverables and tasks that should be undertaken. In addition to the deliverables and tasks identified, you should also add in all other deliverables and tasks you identify as necessary. You should use the RAG status column to monitor and keep under review each of the key deliverables and tasks, and identify where amendments may need to be made to the plan. The filters can be used to sort the information for example by date to show what's due for completion. You may also use the filters to sort for relevant information to be provided at update meetings.
Evaluation
This tab can be used to inform the evaluation of activities. The example content should be adapted to ensure that it reflects the main deliverables and tasks contained in your plan, and assesses whether your stated objectives have been met. The outcome of this evaluation can then be used to feed back into your engagement strategy and project plan, and to help with keeping these under review.
Adjustments log
This tab can be used to keep a record of any changes and updates that are made to your project plan.

## Objectives & success measures
Objectives | Tools for measuring success | Achieved (ü) | Comments / supporting evidence
Run electoral registration activities in accordance with the legislation and guidance | Completion of tasks by deadlines
Project plan reflects key areas set out in guidance
Publication of electoral registers that are as accurate and complete as possible | Completion of tasks by deadlines
Records of data sources used and other methods used to identify persons who do not have an entry in the register; record of subsequent efforts to register them to vote
Public engagement strategy setting out who you need to engage with, how you are going to target them and how you are going to work with internal and external partners to ensure you reach people. In Scotland and Wales, this will need to include how to reach eligible 14 and 15 year olds
Everybody who is entitled to register is able to and registering is as straightforward, accessible and secure as possible | Public engagement strategy and evaluation of public engagement activities
Feedback from electors
Feedback from staff
Professional delivery | Electoral registration project plan
Risk register
Notes of project group meetings
Training schedule and materials
Record of meetings
Contracts in place for any outsourced work
Contingency arrangements
Consistency | Plans
Training schedule and materials
Clear management structures and escalation procedures
Transparency | Clear audit trail for all processes
Arrangements for access/supply of the register

## Resource requirements
Resource requirements
Staffing
Type | Identification | Recruitment | Appointment | Cost estimate
Core team
Temporary staff
Canvassers
Other internal staffing support required from across the organisation (E.g. Communications, frontline/call centre, ICT)
ICT and equipment
Type | Identification | Procurement process | Installation | Cost estimate
Hardware
Equipment - stationery, trays, other office equipment, envelopes, etc.

## Deliverables & tasks
Task ref. | Key deliverables | Sub-deliverable | Detailed tasks | Start date | End date | Comments | RAG status | Owner
| Establish an electoral registration project group |  | Establish who will chair the group, who will be involved and terms of reference
Establish best method of engagement with group
Establish method for recording actions and taking forward actions
| Prepare plans to support the effective delivery of electoral registration | Identify project aims and objectives, and plan for the tasks that will need to be undertaken to achieve these
|  | Update public engagement strategy | Review public engagement strategy (refer to 'Your public engagement strategy and registration plan' in our Running electoral registration guidance).
|  | Identify and manage risks | Develop risk register
| Prepare data for Canvass Data Match | Identify training needs, IT support | Prepare the property database. Establish connection for national data test
| Identification of the required resources | Identify staffing requirements and any necessary recruitment arrangements | Assess staffing requirements for all roles and specific processes. In Scotland and Wales, take into account any additional processes for 14/15 year olds, for example, how you will carry out identity verification for this age group
Assess need to recruit additional staff
Write to any staff you have used previously and are considering re-appointing, checking availability
Appoint staff in line with council's recruitment processes
|  | Identify how you are going to deploy canvassers | Decide for what purposes you will be using canvassers
|  | Check resource assumptions are robust | Ensure appropriate budget is available and will be sufficient to cover planned registration activity.
|  | Review your current electoral / registration structure in light of your experiences | Ensure that staffing resource is sufficient
|  | Review IT systems and arrangements to ensure continued effectiveness during the canvass and in advance of the next scheduled polls | Ensure that IT resource is robust. You should also ensure that your systems are able to process all applications made on the updated forms and, where required, that they are able to email an ITR.
If using any new technologies ensure you undertake a data protection impact assessment to help identify, assess and mitigate risks.
|  | Ensure that all relevant equipment is in place | Review whether current levels of scanners and work stations are adequate or whether additional are needed
|  | Ensure storage requirements are adequate | Carry out assessment of the amount of storage required
Decide on whether to store these forms on or off site and make any necessary arrangements including how you will be able to retrieve them when they are due for destruction, as well as any security requirements to ensure that electors’ personal data is kept safe. In Scotland and Wales, you should factor into your considerations the appropriate storage of any data relating to 14 and 15 year olds.
|  | Decision to print in house or outsource | Review arrangements with printer and ensure that they have capacity to meet your requirements
Review any written contracts / agreements with any contracters processing data on your behalf to ensure they reflect the requirements of current data protection legislation
Ensure risk register covers the complexity and volume of printing and includes relevant mitigation and contingency
| Identification of training needs, incorporating external and internal sources of training | Training of core team | Identification of training needs for all staff - new/existing staff/permenant/temporary staff/canvassers; example refresher training /ensure update to knowledge/skills
Identify method of training e.g. internal or external training/briefing sessions
Prepare training schedule
Take into account any accessibility requirements of staff
Review and prepare required training materials and ensure they reflect data protection requirements
|  | Training of staff for specific processes | Identify what they need to know/skills
Identify method of training e.g. internal or external training/briefing sessions
Prepare training schedule
Take into account any accessibility requirements of staff
Review and prepare required training materials and ensure they reflect data protection requirements
| Implementation of the public engagement strategy | Identify how direct contact with residents will be managed | Identify and allocate tasks to individuals
Develop mechanisms for tracking and evaluating progress made
| Administer the canvass | Send canvass communications to all properties and carry out the necessary follow-up processes | Identify canvass routes for all properties Send e-communications and/or CCAs to Route 1 properties Make at least three contact attempts to Route 2 properties, including sending a canvass form and making personal contact Make contact with any Route 3 properties
Send ITRs to newly identified electors, including by email where requested, and carry out the necessary follow-up processes
Publish the electoral register
|  | Review processing activites and consider any measures that need to be put in place to demostrate compliance with current data protection legislation | Undertake an audit of all personal data that you will collect and determine and document the lawful basis on which you are collecting / processing it.
| Identify new electors | Use available local data to identify and target potential electors and to verify and validate data held on your register | Identify the records you are entitled to inspect
Plan how you will use the records to identify and verify entries on the register In Scotland and Wales, plan how you will verify the identity of all 14 and 15 year olds
Keep record of data sources checked to demonstrate compliance with data protection prinicples
|  | Make the necessary house-to-house enquiries to identify and target potential electors and to verify and validate data held on your register. In Scotland and Wales, the duty to make house-to-house does not apply in relation to 14 and 15 year olds | Identify where house-to-house enquiries and personal visits will be necessary
Plan how the necessary steps under 9A of RPA 1983 will be carried out
| Ensure those no longer entitled to be registered are removed from the register | Identify and use available data sources that will prompt further investigation as to whether an elector is entitled to remain registered | Where necessary obtain two different sources of information before an elector's entry on the register may be deleted
Arrangements in place to conduct registration reviews
| Management of contractors and suppliers, including printers and software suppliers | Review arrangements in place with printers | Assess whether outsourcing is required through a cost-benefit analysis
Create specification setting out exactly what is required and by when
Liaise with council procurement team to ensure approach to procurement complies with correct legal process
Commence procurement process or choose a contractor from the council’s list of approved contractors
Develop written contract(s) with legal and/or other expert advice
Ensure that data protection is integral in any tender exercise and satisy yourself that any existing contracters and suppliers are aware of their obligations under current data protection legislation
|  | Review arrangements in place with software suppliers | Ensure systems are in place
Ensure support mechanisms are available in case of software failure
| Processes to identify any patterns of activity that might indicate potential integrity problems, including what steps are to be taken to deal with any such problems | Maintain a good working relationship with local police Single Point Of Contact (SPOC) | Make contact with local police SPOC
Schedule regular communications
Agree trigger points for when matters should be reported to police SPOC, including threshold number of absent vote applications being directed to any one address
Provide training/guidance notes to all staff involved in registration and supervision of the register on how to spot potential fraud and what actions should be taken
Put in place procedures for sending electoral data securely
| Mechanisms for monitoring and evaluating your progress with delivering your plans and for recording amendments to your plans or public engagement strategy |  | Identify key areas to be evaluated and when
| Manage absent vote applications and the sending of postal vote identifier rejection notices | Ensure that all electors can access the absent vote process | Work with Comms team to identify communication channels for promoting absent voting options
Implement communications plan
|  | Administer absent voting processes | Process applications
Maintain absent vote records and lists
Undertake postal vote refresh/reapplication process (as relevant)
Undertake proxy vote refresh
Send postal vote identifier rejection notices after elections
| Administer the Voter Authority Certificate and Anonymous Elector's document process | Develop an engagement strategy for those less likely to hold an accepted form of ID | Identify those less likely to have an accepted form of ID
Work with Comms team to identify appropriate communication channels
Implement engagement strategy
|  | Process applications for VACs and AEDs | Process applications
Manage production and distribution of temporary VACs
Manage production and distribution of AEDs

## Dependencies & partners
Contacts
Internal service providers
Department / service | Contact name | Phone number | Email address
IT department
Finance team
Data holders
Data protection officer
Call centre / reception
Communications / media
HR
Education department
External service providers
Company | Contact name | Phone number | Email address
Software supplier
Hardware supplier
Printers
Specialist stationery suppliers
Royal Mail
Public engagement partners
Organisation | Contact name | Phone number | Email address
Local youth groups
Schedule of meetings
Meeting type | Date | Actions | Owner

## Evaluation
Key areas to be evaluated | What is working well | Are the objectives being met | Issues that need to be addressed | Key recommendations (to be reflected back in registration plan and public engagement strategy) | To be completed by (date) | Owner
Public engagement activity e.g. effectiveness and impact of activities
Equipment and stationery e.g. Estimates of required forms
Printers e.g. quality, timescales, price, communication
Software performance e.g. performance of software, identification of any changes required to ease processing, supplier’s response to any issues
Management of contractors e.g. performance of contractors: communication, effectiveness of contracts, value for money
Recruitment and training (temporary and permanent) e.g. was the training effective, were the staff efficient
Processing/handling of queries e.g. adequacy of FAQs, complaints recording process
Resources e.g. staffing levels, availability of resources
Integrity e.g. any problems that arose, comments/feedback from SPOC

## Adjustments log
Date | Details of change | Reason | Authorising Officer