## Front cover
Electoral registration risk register
Date:
Author:
Document version:
Reviews
Name | Role | Date | Sign-off (ü)

## How to...
How to use this template
This risk register template provides some example risks and suggestions for mitigating them. It does not include an exhaustive list of risks, which will be dependent on your local circumstances and the processes you have in place. In addition to the risks identified in the template you should identify any other risks, including ones specific to your local circumstances , and how you would mitigate those. This template also provides a template issues register to log any issues that arise and subsequent action taken.
Defining the level of impact and likelihood of risk
Inherent risk evaluation
How likely is it that the risk going to happen?
· Unlikely – Likelihood of occurrence is relatively slim - <10% chance of occurrence
· Possible – Quite possible that the risk could occur especially if control measures are inadequate - 10% - 50% chance of occurrence
· Probable – More likely to happen than not - >50% chance of occurrence
What would the impact be if the risk was to crystallise?
· Minor – Unlikely to have a permanent or significant effect
· Moderate – Potential impact on performance and service delivery. May be adequately managed through existing processes
· Significant – Severe impact on performance through a reduced ability to deliver.
The 3x3 matrix below can be used to calculate the overall risk score:
| IMPACT | 3 | 3 | 6 | 9
|  | Significant | (Significant & Unlikely) | (Significant & Possible) | (Significant & Probable)
|  | 2 | 2 | 4 | 6
|  | Moderate | (Moderate & Unlikely) | (Moderate & Possible) | (Moderate & Probable)
|  | 1 | 1 | 2 | 3
|  | Minor | (Minor & Unlikely) | (Minor & Possible) | (Minor & Probable)
|  |  | 1 - Unlikely | 2 - Possible | 3 - Probable
LIKELIHOOD
Residual risk evaluation
Once the appropriate action has been identified to address an individual risk, the action is given a score of 1 to 3 based on an assessment of how likely it is to be effective in reducing the risk (not all risks are capable of being reduced).
The risk owner will need to make an assessment as to whether the control measures are:
· Good: Would score a 3, i.e. control measures are fully in place, agreed by line manager and form part of everyday activity
· Average: Would score a 2, i.e. some controls in place but further actions to be planned and/or executed
· Poor: Would score a 1, i.e. no control measures in place as yet, although actions may be planned
The initial (inherent) risk score is then divided by the score for the control action to give a residual risk score. This is the ultimate assessment of the scale of the risk and whether it is Red, Amber or Green.

## Risk register
Number | Risk | Cause | Impact description | Likelihood | Impact | Inherent rating | Mitigation / current controls | Control Score | Residual Rating | Further action required | Lead Officer | Date of completion
PLANNING
| Failure to ensure proper plans and strategies are in place | No comprehensive written plan for electoral registration activity or public engagement strategy | Necessary actions not completed or completed late |  |  | 0 | Prepare and keep under review a plan for electoral registration activity and a public engagement strategy to ensure all necessary activities are planned for and sufficient resources are available as and when required |  | #DIV/0!
|  | Poor planning assumptions | Missed deadlines |  |  | 0 | Ensure lessons learnt from previous registration activity are incorporated into the planning process. In Scotland and Wales, this includes lessons learnt in relation to the registration of 14-15 year olds |  | #DIV/0!
|  | Lessons learnt from previous registration activity not incorporated into planning. In Scotland and Wales, this includes lessons learnt in relation to the registration of 14-15 year olds | Potential breach of legislation |  |  | 0 |  |  | #DIV/0!
| Insufficient resources | Insufficient budget allocated | Unable to meet statutory responsibilities |  |  | 0 | Identify projected costs to meet implementation plan early on in the planning process |  | #DIV/0!
|  | Insufficient funding available | Planned activities not completed on time |  |  | 0 | Set up regular meetings with Finance to plan for electoral registration activity funding requirements |  | #DIV/0!
|  | Insufficient staffing resources | Inability to demonstrate readiness |  |  | 0 | Review staffing levels and start engaging with HR teams to ensure recruitment lead times are managed to secure appropriate staff on time. |  | #DIV/0!
LOSS OF PREMISES
| Loss of electoral registration office | Office affected by flood, fire vandalism, etc. | Unable to process forms |  |  | 0 | Check council’s emergency plan for relocation and security arrangements, and identify alternative temporary accommodation |  | #DIV/0!
|  |  | Loss of data |  |  | 0 | Ensure daily back-up of data held off-site |  | #DIV/0!
FAILURE OF IT PROVISION
| Loss of IT capability | System or network failure | Inability or delay in sending data to the digital service |  |  | 0 | Perform daily back-ups and download documentation onto disc for secure storage off-site |  | #DIV/0!
|  |  | Unable to verfiy identity of applicants |  |  | 0 | Check with electoral registration software supplier with regards to availability of duplicate system |  | #DIV/0!
|  |  | Delay in processing applications and the ability to send ITRs by email |  |  | 0 | IT provider to ensure support |  | #DIV/0!
[6 empty] | 0 | Emergency generator provision by IT provider |  | #DIV/0!
[6 empty] | 0 | Regular maintenance/service of scanners and other hardware |  | #DIV/0!
[6 empty] | 0 | Engage with local IT team, digital service and EMS suppliers where issues are anticipated ASAP |  | #DIV/0!
ENGAGEMENT AND VOTING
| Electoral registration process is not accessible | Unable to reach hard to reach groups | Voters unable to register or to vote by chosen method (i.e. postal or proxy) |  |  | 0 | Consider demography of the local authority area and the lessons learnt from previous registration activity |  | #DIV/0!
|  | Information is provided in one format with no account taken of the needs of different audiences | Electoral register incomplete |  |  | 0 | Maintain public engagement strategy |  | #DIV/0!
[6 empty] | 0 | Ensure all staff are aware of disability equality duties (for example, by attending disability equality training) |  | #DIV/0!
| Queries unable to reach electoral staff | Telecom/IT failure | Lack of information |  |  | 0 | Ensure dedicated line to electoral registration office, plus mobile numbers made available as back up |  | #DIV/0!
|  | Large volume of calls during the canvass/in the lead up to an election | Voters unable to register to vote |  |  | 0 | Seek out use of other fax machines within building to use if necessary |  | #DIV/0!
[6 empty] | 0 | IT provider to ensure support, particularly on critical days |  | #DIV/0!
|  |  | Wrong advice given |  |  | 0 | Emergency generator provision by IT provider |  | #DIV/0!
[6 empty] | 0 | Ensure all outgoing information contains electoral registration office contact details |  | #DIV/0!
[6 empty] | 0 | Provide frontline staff with FAQs, with complex enquiries referred to core registration staff |  | #DIV/0!
| Registration applications do not reach office before the deadlines | Telecom/IT failure | Voter confusion |  |  | 0 | Ensure dedicated line to electoral registration office, plus mobile numbers made available as back up |  | #DIV/0!
|  | Failure of IER digital service /ERO Portal | Voters unable to register to vote |  |  | 0 | IT provider to ensure support, particularly on critical days |  | #DIV/0!
|  |  | Disenfranchisement |  |  | 0 | Emergency generator provision by IT provider |  | #DIV/0!
|  | Wrong advice given | Damage to council's reputation |  |  | 0 | Provide frontline staff with FAQs, with complex enquiries referred to core registration staff |  | #DIV/0!
|  | Lack of information | Complaints |  |  | 0 |  |  | #DIV/0!
| ERO unable to verfiy registration applications | Failure of IER digital service /ERO Portal | Disenfranchisement |  |  | 0 | Ensure access to local data matching sources are readily available
|  |  | Voters unable to vote |  |  | 0 | Proactively contact applicants to provide evidence / attestation to support the application
|  |  | Complaints |  |  | 0 | Public awareness strategy to make provision for communication of key information, including deadlines |  | #DIV/0!
| Absent vote applications do not reach office before the deadlines | Telecom/IT failure | Voter confusion |  |  | 0 | Ensure dedicated line to electoral registration office, plus mobile numbers made available as back up |  | #DIV/0!
| Voter Authority Certificate applications to do not reach the office before the deadline | Wrong advice given | Voters unable to vote by chosen method (i.e. postal or proxy) |  |  | 0 | Seek out use of other fax machines within building to use if necessary |  | #DIV/0!
|  | Lack of information | Disenfranchisement |  |  | 0 | IT provider to ensure support, particularly on critical days |  | #DIV/0!
|  |  | Registered voters without acceptable photographic ID unable to vote |  |  | 0 | Emergency generator provision by IT provider |  | #DIV/0!
[6 empty] | 0 | Provide frontline staff with FAQs, with complex enquiries referred to core registration staff |  | #DIV/0!
[6 empty] | 0 | Public awareness strategy to make provision for communication of key information, including deadlines |  | #DIV/0!
| Large volume of Voter Authority Certificates and/or Anonymous Elector's Documents close to deadline. | Lots of publicity, particularly around deadlines. | Voters unable to vote / disenfranchisement |  |  | 0 | Ensure sufficinet,trained staffing levels to manage peak volumes |  | #DIV/0!
|  |  | Registered voters without acceptable photographic ID unable to vote |  |  | 0 | Public awareness strategy to make provision for communication of key information, including deadlines |  | #DIV/0!
|  | Public misunderstanding about all the different acceptable forms of photographic ID. | Voters unable to vote / disenfranchisement |  |  | 0 | Public awareness strategy to make provision for communication of key information, including deadlines |  | #DIV/0!
|  |  | Registered voters without acceptable photographic ID unable to vote |  |  | 0 | Provide frontline staff with FAQs, with complex enquiries referred to core registration staff |  | #DIV/0!
E | Absent vote applications received close to deadline and not verified before set deadline | Failure of IER digital service /ERO Portal | Voter unable to vote by chosen method (i.e. postal or proxy) |  |  | 0 | Ensure access to local data matching sources are readily available |  | #DIV/0!
|  | Elector fails to provide evidence for exceptions process | Voter unable to vote by chosen method (i.e. postal or proxy) |  |  | 0 | Proactively contact applicants to provide evidence / attestation to support the application |  | #DIV/0!
|  | Lots of publicity, particularly around deadlines. | Disenfranchisement |  |  | 0 | Ensure processes are in place to deal with the late issue of postal votes |  | #DIV/0!
|  | Public misunderstanding about the changes to the absent vote application process |  |  |  | 0 | Communication with voters about the new requirements for absent vote applications |  | #DIV/0!
| Messages are misrepresented | Inadequate partnership work | Voter confusion |  |  | 0 | Clearly set out and agree timings and messages |  | #DIV/0!
|  |  | Complaints |  |  | 0 | Establish regular communications |  | #DIV/0!
[6 empty] | 0 | Agree an approach to evaluation of the activity |  | #DIV/0!
FAILURE ON THE PART OF CONTRACTORS
| Non/late delivery and return of forms | Missed printing deadlines or non-completion | Forms are not received and individuals are not registered |  |  | 0 | Early discussions with printers at national and local level to identify any obvious clashes and discuss contingencies |  | #DIV/0!
|  | Printing errors |  |  |  | 0 | Check out performance of potential suppliers with other clients and consider visiting premises of the selected contractor to inspect capacity, set up and processes |  | #DIV/0!
[6 empty] | 0 | Where the contractor is processing personal data on your behalf, ensure that data protection is integral to the procurement process |  | #DIV/0!
[6 empty] | 0 | Prepare and agree contracts as soon as possible and regularly monitor performance against expectations |  | #DIV/0!
[6 empty] | 0 | Where the contractor is processing personal data on your behalf, ensure that a written contract/agreement is in place with the processor in accordance with data protection legislation |  | #DIV/0!
|  | Postal strike |  |  |  | 0 | Close liaison with contractor to identify potential problems in advance |  | #DIV/0!
[6 empty] | 0 | Forecasted print volumes based on the previous canvass shared with print suppliers to enable planning |  | #DIV/0!
[6 empty] | 0 | Ensure robust proofing procedures are in place and include quality checking mechanisms in contract or in any in-house arrangements prior to issue of forms |  | #DIV/0!
[6 empty] | 0 | Consider contingency arrangements to print elsewhere in the event of non-completion |  | #DIV/0!
[6 empty] | 0 | Close liaison with account manager at Royal Mail/other service provider |  | #DIV/0!
[6 empty] | 0 | Consider alternative options for distribution e.g. by hand using in-house teams or by an alternative service provider |  | #DIV/0!
[6 empty] | 0 | Consider promoting potential to apply online |  | #DIV/0!
INTEGRITY ISSUES
| False information is given on form | Electoral fraud | Integrity of register/ (and ultimately election) is called into question |  |  | 0 | Create and keep updated an integrity plan |  | #DIV/0!
|  | Mistake by applicant | ERO’s ability called into question (reputational risk) |  |  | 0 | Brief staff processing forms on checking procedures |  | #DIV/0!
[6 empty] | 0 | Schedule regular communications with local police SPOC and agree trigger points for referral |  | #DIV/0!
[6 empty] | 0 | Provide training/guidance notes to all staff involved in registration on how to spot potential fraud and what actions should be taken |  | #DIV/0!
| Unauthorised access to electoral register/ application forms | Procedures not in place | Integrity of register/ (and ultimately election) is called into question |  |  | 0 | Ensure documents are kept in secure location |  | #DIV/0!
|  |  | ERO’s ability called into question (reputational risk) |  |  | 0 | Issue guidance notes / EC rescource to recipients |  | #DIV/0!
| Taking of electronic notes or other means of unauthorised copying of electoral register | Inadequate guidance to staff | Integrity of register/ (and ultimately election) is called into question |  |  | 0 | Provide training and guidance notes to supervising staff |  | #DIV/0!
|  |  | ERO’s ability called into question (reputational risk) |  |  | 0 |  |  | #DIV/0!
STAFFING
| Mistakes by inexperienced staff or by staff not fully aware of legislation /procedure | Lack of availability of experienced staff | Errors processing registration forms and/or absent vote applications |  |  | 0 | Pre-application consultation with established canvassers to assess availability and willingness to work during the required period |  | #DIV/0!
| Mistakes made by staff not aware of legislative changes | Inadequate/lack of training | Possible disenfranchisement of electors |  |  | 0 | Training to be scheduled for all staff to ensure they are provided with the necessary information to be able to undertake their duties, including data protection considerations |  | #DIV/0!
[6 empty] | 0 | Provide resources/support materials such as guidance notes to relevant staff |  | #DIV/0!
[6 empty] | 0 | Monitor work of staff |  | #DIV/0!
[6 empty] | 0 | Ensure a robust quality checking process before publication of register |  | #DIV/0!
| Unable to appoint sufficient staff | Insufficient/non-provision of resources | Insufficient staff to cover processes |  |  | 0 | Seek alternative sources of recruitment – e.g. community groups |  | #DIV/0!
|  | Difficulty in recruiting suitable staff | Unable to carry out house-to-house enquiries as required by law |  |  | 0 | Ensure sufficient staff have been identified and allocated to all electoral processes |  | #DIV/0!
[6 empty] | 0 | Consider training additional staff as a contingency |  | #DIV/0!
[6 empty] | 0 | Review remuneration arrangements (e.g. phased payments) |  | #DIV/0!
[6 empty] | 0 | Pre-application consultation with established canvassers to asses availability and willingness to work during the required period |  | #DIV/0!
| Loss of staff | Sickness | Insufficient number of staff to cover processes |  |  | 0 | Ensure list of trained, reserve staff with contact numbers is in place |  | #DIV/0!
|  | Outbreak of pandemic or other contagious illness affecting large numbers of staff | Unable to carry out house-to-house enquiries as required by law |  |  | 0 | Consider asking existing canvassers to take on additional work |  | #DIV/0!
[6 empty] | 0 | Provide appropriate training and guidance notes to staff who have been re-deployed and are carrying out unfamiliar tasks |  | #DIV/0!
[6 empty] | 0 | Consult with local authority’s contingency planning unit |  | #DIV/0!
[6 empty] | 0 | Have processes in place to minimise the risk of cross-infection, taking into consideration any advice provided by the Department of Health |  | #DIV/0!
| Insufficient support staff appointed | No detailed assessment of staffing requirements | Inability/ difficulty in meeting deadlines |  |  | 0 | Map-out staffing requirements at an early stage in project planning process |  | #DIV/0!
|  |  | Mistakes by overworked staff |  |  | 0 | Consider need to appoint temporary support staff to assist the core team at different points of the process |  | #DIV/0!
| A threat to canvasser safety | Canvassers encounter problems with elector dissatisfaction or aggressive behaviour whilst trying to call at a property | Staff feel threatened and are unable to carry out their role |  |  | 0 | Undertake a risk assessment of canvassing areas |  | #DIV/0!
|  | Poor weather and/or canvassing during hours of darkness increasing possibility of accident or injury | Unable to recruit sufficient canvassers willing to work during hours of darkness or winter period |  |  | 0 | Refer to lone working policy/procedures |  | #DIV/0!
[6 empty] | 0 | Considering canvassing in pairs |  | #DIV/0!
[6 empty] | 0 | Provide guidance and training to canvassers, including on weather-related or darkness-related health and safety issues and dealing with difficult circumstances |  | #DIV/0!
[6 empty] | 0 | In planning canvass activity consider how to minimise threats to health and safety, such as minimising the amount of canvassing taking place after dark and carrying out more weekend canvassing |  | #DIV/0!
[6 empty] | 0 | Ensure appropriate insurance arrangements are in place for canvassers |  | #DIV/0!
VERIFICATION
| Difficulties accessing data to undertake data-matching with local data sources (where intended) | Local data sources not compatible | Inability to undertake effective local data matching as planned |  |  | 0 | Engage data holding teams and departments early. In Scotland and Wales, ensure you engage local education departments. |  | #DIV/0!
|  | Access to local data sources is restricted by organisation policies or contracts where this is held by third parties | Increased number of electors who need to provide documentary evidence |  |  | 0 | Seek agreement to share data early in order to give data holding departments time to secure release of data. |  | #DIV/0!
[6 empty] | 0 | Ensure that you maintain records of the data sources you have inspected in order to demonstrate that you are complying with the principles of processing personal data, ensuring that it is processed lawfully, fairly and in a transparent manner |  | #DIV/0!
|  |  | In Scotland and Wales, inability to verify the identity of 14/15 years olds without access to education records or other local data |  |  | 0 | Share or seek out experiences of other authorities who have successfully accessed local data sets. |  | #DIV/0!
DATA SECURITY
| Failure to put in place adequate security arrangements | Inadequate security of personal data (NINos/DoB) within electoral registration and absent voting records | Breach of legislation |  |  | 0 | Liaison with local authority data security expert. In Scotland and Wales, seek their expertise in relation to the handling of personal data of 14/15 year-olds |  | #DIV/0!
|  | Poor security of personal data (NINos/DoB) held on hard copy registration forms by canvassers | Reputational damage |  |  | 0 | Review office accommodation and storage requirements and access to these areas. In Scotland and Wales, take account of the need to securely store and handle personal data belonging to 14/15 year-olds, particularly given legislative restrictions on use |  | #DIV/0!
[6 empty] | 0 | Ensure you are registered as a data controller independent to your council, and have appropriate privacy notices in place and visable. |  | #DIV/0!
[6 empty] | 0 | Ensure your document retention policy is up-to-date, covers every document you process, and that you and your staff adhere to it. In Scotland and Wales, ensure that it takes account of handling personal data belonging to 14/15 year-olds |  | #DIV/0!
[6 empty] | 0 | Ensure that data protection is integral to any new or existing contracts or data-sharing agreements, with clear agreements on how data is to be transmitted, stored and destroyed |  | #DIV/0!
[6 empty] | 0 | Ensure you have procedures in place to detect, report and investigate any personal data breach |  | #DIV/0!
[6 empty] | 0 | Ensure canvassers are aware of data security importance/requirements and that data protection is reflected in their training In Scotland and Wales, ensure all those handling data relating to 14/15 year-old attainers are aware of the legal requirements |  | #DIV/0!
[6 empty] | 0 | Provide clear instructions to canvassers on handling and storing information In Scotland and Wales, provide specific instructions on safeguarding data relating to 14/15 year olds |  | #DIV/0!

## Issue register
This issues register can be used to record any issues arising. The log should cover the nature of the issue, its source, the date it was raised and its potential impact. It should also include the proposed action to deal with the issue, as well as assigning clear ownership to the issue and establishing the date of its anticipated resolution.
An issue which has occurred is usually the result of an earlier risk which has now become a reality, therefore it is vital to ensure that both the issues register and risk register are live documents and that they are regularly reviewed and updated.
Issue (already occurred) | Issue source (Where/Who raised) | Date issue arose | Potential impact (1-3) | Action | Issue owner | Target date for resolution (completion date in brackets) | Status – Open/ Closed